## Read me
Field | Value
Title | Sprint 3 UAT preparation pack
Prepared | 2026-10-25
Scope | All Sprint 1 and Sprint 2 work, plus Function 7 View As and a simple system-use FAQ chatbot. No feature-selection exercise or silent deferral.
Target | Wednesday: reviewed, execution-ready UAT pack and an evidence-backed rehearsal/readiness report. This is not a promise of product acceptance by Wednesday.
Status | Local QA working draft. Scope follows Josh; scenario detail and new task allocations are proposed working instructions, not customer approval.
Execution Status | Not Run. No product, UAT rehearsal, live environment, or business acceptance was tested while preparing this pack.
Notes | No day-by-day timeline is included.
Notes | The available Product Backlog V3 contains US-001 through US-053 but says Sprint TBD. All 53 are retained conservatively; neither Done nor Backlog removes coverage. Josh should attach the actual Sprint 1/2 delivery mapping without dropping an item silently.
Notes | R6 budget/statistics requirements are retained separately because the story list does not fully represent them. ADD-VIEW-AS and ADD-FAQ are local coverage labels, not official user-story IDs.
Notes | Priority of FAS in the customer meeting changes execution order, not scope. School, class and student functions remain in the pack.
Notes | Each row is a business acceptance scenario, not a replacement for the detailed functional, security, API or regression suites. Story mapping means planned coverage, never proof of test completeness or a pass.
Notes | UAT-D identifiers are local expected-behaviour/readiness questions. They do not reopen delivery scope, allocate official defects or replace existing D-01 to D-16 questions in the F2 plan.
Notes | Resolve referenced questions and record the chosen rule, approver and source before scoring the affected scenario. Keep unaffected scenarios runnable. No conditional pass is allowed.
Notes | Scenarios use local UAT identifiers. Preserve existing TC/TS/BUG identifiers when linking team records; do not renumber them.
Notes | Execute only on an authorized isolated QA build with synthetic data and approved reset controls. No financial operation here authorizes shared or production changes.
Notes | Use a dated execution copy of the workbook. Keep definitions separate from results. Record build, actor, date, actual outcome, evidence and linked defects for each run.
Notes | All examples and numerical outcomes below are QA fixture proposals. BA must check contract-dependent expected results before business UAT; they are not production policy.
Notes | Business users make the acceptance decision. QA/BA-only execution is a rehearsal unless explicit acceptance authority is recorded.
Coverage rows | 66
Scenarios | 49
Steps | 151
Status meanings | Passed: observed expected result. Failed: observed result differs. Blocked: a prerequisite prevented execution. Not Run: no execution recorded.
Coverage warning | Story mapping is planned traceability, not proof of completeness or a pass.
Using this workbook | Run each Script steps action and compare with its observable expected result. Use a dated execution copy; record status, actual result, evidence, defect, executor, date and build in Scenarios. Keep this reusable planning workbook blank. --check intentionally rejects executed copies.

## Assignments
Person | Responsibilities | Basis | Reviewer
Josh | Lead; R1 lifecycle and R2 top-up; combine journeys; reconcile rules with BA; confirm build, business acceptance authority and final readiness report. | Existing R1/R2 QA responsibility; lead coordination. No external send or shared-board change authorized. | Gavin
Kent | R3 fees and charge generation; school-side SBFAS scheme, subsidy matrix and manual review. Supply charge/scheme handoffs to Howard and Gavin. | Padlet: Function 3 plan and fee-module testing with Chan. School-side FAS is the proposed Sprint 3 extension accepted for preparing this pack. | Chan
Chan | Environment, roles, data mapping/reset; R3 school/student/enrolment and CSV import; paper FAS/OCR; lead View As with function-owner checks. | Padlet: QA environment, R8 login automation and R3 fee testing with Kent. Paper FAS/View As are new planning allocations. | Kent
Howard | Parent login/linkage/home/history/profile; online FAS submission and details; FAQ answer bank and checks; common scenario format. | Padlet: Function 8 review and common case/defect templates. Online FAS/FAQ are new planning allocations. | Gavin
Gavin | R9 payment/receipts/failure recovery; FAS assessment and subsidy calculations; R6 budget/statistics; reconcile end-to-end money with Kent and Josh. | Padlet: Function 9 review and R4 synthetic income-data task, not ownership of all FAS. Assessment/R6 are new planning allocations. | Howard

## Coverage
ID | Title | Area | Owner | Source references | Source locator | Scenario IDs | Decision IDs
US-001 | Initial Synchronization & EA Creation | R1 - EA Lifecycle | Josh | • SRC-BACKLOG | Product Backlog row 6; R1 ¦ Initial Synchronization & EA Creation • Bullet B01, B03–B07 | • UAT-001 | • UAT-D03
US-002 | Daily Incremental EA Provisioning | R1 - EA Lifecycle | Josh | • SRC-BACKLOG | Product Backlog row 7; R1 ¦ Initial Synchronization & EA Creation • Bullet B02–B08 | • UAT-002 | • UAT-D03
US-003 | Account Eligibility Verification & Closure | R1 - EA Lifecycle | Josh | • SRC-BACKLOG | Product Backlog row 8; R1 ¦ Tự động đóng TK EA • Bullet B01–B09 | • UAT-003 | • UAT-D03
US-004 | CPF Transfer of Residual EA Funds | R1 - EA Lifecycle | Josh | • SRC-BACKLOG | Product Backlog row 9; R1 ¦ Chuyển tiền dư qua CPF • Bullet B01 R1 ¦ CPF Transfer • Bullet B01 | • UAT-004 | • UAT-D03
US-005 | SingPass Login & Parent-Child Linkage | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 10; R8 ¦ SingPass Login & Parent–Child Linkage • Bullet B01–B08 | • UAT-005
US-006 | Parent Home & EA Balance Overview | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 11; R8 ¦ View Education Account • Bullet B01, B03, B06 | • UAT-006 | • UAT-D03
US-007 | Linked Child Enrolment View | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 12; R8 ¦ View Education Account • Bullet B02, B06 R3 School ¦ F10 – Student Enrolment Overview • Bullet B05 | • UAT-006 | • UAT-D03
US-008 | EA Transaction History & Filters | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 13; R8 ¦ View Education Account • Bullet B03–B04 R9 ¦ Outstanding Fees & Payment • Bullet B03 | • UAT-006 | • UAT-D03
US-009 | Update Parent Contact Information | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 14; R8 ¦ Update Basic Personal Details • Bullet B01–B06 | • UAT-007
US-010 | FAS Grant Information Display | R8 - Parent Portal | Howard | • SRC-BACKLOG | Product Backlog row 15; R8 ¦ View Education Account • Bullet B05 | • UAT-008 • UAT-045 • UAT-046 • UAT-049 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-011 | Outstanding Invoices & Fee Details | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 16; R9 ¦ Outstanding Fees & Payment • Bullet B01–B04 | • UAT-009 • UAT-045 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-012 | Education Account Payment | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 17; R9 ¦ Outstanding Fees & Payment • Bullet B04–B05, B08, B10 | • UAT-010 | • UAT-D03
US-013 | Sandbox Online Payment | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 18; R9 ¦ Outstanding Fees & Payment • Bullet B04, B06, B09–B10 | • UAT-011 | • UAT-D09
US-014 | EA and Online Split Payment | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 19; R9 ¦ Outstanding Fees & Payment • Bullet B07–B10 | • UAT-012 • UAT-045 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-015 | Payment Results & Receipts | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 20; R9 ¦ Outstanding Fees & Payment • Bullet B10 | • UAT-010 • UAT-011 • UAT-045 | • UAT-D03 • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-016 | F01 - School Master Data | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 21; R3 School ¦ F01 – School Management • Bullet B01–B06 R3 School ¦ F02 – School User Account & School Assignment • Bullet B01 | • UAT-013
US-017 | F02 - School User Authorization / Assignment | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 22; R3 School ¦ F01 – School Management • Bullet B05 R3 School ¦ F02 – School User Account & School Assignment • Bullet B01–B02 | • UAT-014 • UAT-048 | • UAT-D04 • UAT-D09
US-018 | F02 - School User First Login Profile | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 23; R3 School ¦ F02 – School User Account & School Assignment • Bullet B02 | • UAT-014 | • UAT-D09
US-019 | F03 - Academic Year, Level & Class Setup | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 24; R3 School ¦ F03 – Academic Year, Education Stage & Academic Level Configuration • Bullet B01–B13 | • UAT-015
US-020 | F05 - Student Record Creation & Maintenance | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 25; R3 School ¦ F05 – Student Record Creation & Management • Bullet B01–B09, B14–B15 | • UAT-015
US-021 | F08 - Student to EA Identity Linkage | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 26; R3 School ¦ F05 – Student Record Creation & Management • Bullet B10–B14 R3 School ¦ F08 – Student–Education Account Linkage • Bullet B01–B06 | • UAT-015
US-022 | F06 - Class Assignment & Enrolment Creation | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 27; R3 School ¦ F06 – Student Enrolment • Bullet B01–B09 | • UAT-016 | • UAT-D10
US-023 | F07 - Class, Level & Year Changes | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 28; R3 School ¦ F07 – Student Transfer & Class Change • Bullet B01, B04–B06 | • UAT-016 | • UAT-D10
US-024 | F07 - Inter-School Transfers | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 29; R3 School ¦ F07 – Student Transfer & Class Change • Bullet B02–B06 | • UAT-017 | • UAT-D10
US-025 | F10 - Enrolment Detail & History Overview | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 30; R3 School ¦ F10 – Student Enrolment Overview • Bullet B01–B06 | • UAT-016 • UAT-017 | • UAT-D10
US-026 | F09 - Academic Structure CSV Import | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 31; R3 School ¦ F09 – Bulk CSV Import for Academic Setup & Student Management • Bullet B01–B03, B06–B10 | • UAT-018 | • UAT-D10
US-027 | F09 - Student & Class CSV Import | R3 - School & Student | Chan | • SRC-BACKLOG | Product Backlog row 32; R3 School ¦ F09 – Bulk CSV Import for Academic Setup & Student Management • Bullet B04–B10 | • UAT-018 | • UAT-D10
US-028 | Individual EA Top-Up | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 33; R2 ¦ Individual Top-Up • Bullet B01–B07 | • UAT-022 • UAT-048 | • UAT-D01 • UAT-D03 • UAT-D04 • UAT-D09
US-029 | Bulk Campaign Rules & Funding Limit | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 34; R2 ¦ Bulk Top-Up Rule Configuration • Bullet B01–B18 | • UAT-023 • UAT-026 | • UAT-D01 • UAT-D02 • UAT-D09
US-030 | Bulk Eligibility Preview & Confirmation | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 35; R2 ¦ Bulk Top-Up Preview & Confirmation • Bullet B01–B06 | • UAT-023 | • UAT-D01
US-031 | Bulk Top-Up Execution & Results | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 36; R2 ¦ Bulk Top-Up Execution • Bullet B01–B07 R2 ¦ Top-Up History & Results • Bullet B05 | • UAT-024 • UAT-025 • UAT-026 | • UAT-D01 • UAT-D02 • UAT-D09
US-032 | Individual & Bulk Top-Up History | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 37; R2 ¦ Top-Up History & Results • Bullet B01–B06 | • UAT-022 • UAT-024 • UAT-025 | • UAT-D01 • UAT-D02 • UAT-D03 • UAT-D09
US-033 | Incorrect Manual Top-Up Correction | R2 - Top-Up | Josh | • SRC-BACKLOG | Product Backlog row 38; R2 ¦ Top-Up History & Results • Bullet B06 R2 ¦ Incorrect Manual Top-Up Correction • Bullet B01 | • UAT-027 | • UAT-D01
US-034 | HQ Shared Fee Catalogue | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 39; R3 Fee ¦ Proposed MVP Fee Master Data • Bullet B01–B13 R3 Fee ¦ Fee Type & Fee Component Management • Bullet B01–B16, B18–B21 | • UAT-019
US-035 | School-Specific Fee Catalogue & Extensions | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 40; R3 Fee ¦ Proposed MVP Fee Master Data • Bullet B14–B23 R3 Fee ¦ Fee Type & Fee Component Management • Bullet B02–B21 | • UAT-019
US-036 | HQ Fee Rates & Effective Periods | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 41; R3 Fee ¦ Fee Rate Configuration • Bullet B01–B19 | • UAT-020 | • UAT-D10
US-037 | Fee Publication & Target Setup | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 42; R3 Fee ¦ Fee Publication & Target Configuration – Các quy tắc cập nhật • Bullet B01–B06, B10–B11 | • UAT-021 | • UAT-D10
US-038 | Pre-Publication Fee Preview | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 43; R3 Fee ¦ Fee Publication & Target Configuration – Các quy tắc cập nhật • Bullet B07–B08 R3 Fee ¦ Student Charge Generation • Bullet B01–B02 R3 Fee ¦ Student Charge Viewing & Management • Bullet B12–B13 | • UAT-021 | • UAT-D10
US-039 | Publish Fees & Generate Student Charges | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 44; R3 Fee ¦ Fee Publication & Target Configuration – Các quy tắc cập nhật • Bullet B08–B09 R3 Fee ¦ Student Charge Generation • Bullet B01–B06 R3 Fee ¦ Student Charge Viewing & Management • Bullet B01–B14 | • UAT-021 | • UAT-D10
US-040 | Issued Student Charges & Cross-Module Access | R3 - Fee Management | Kent | • SRC-BACKLOG | Product Backlog row 45; R3 Fee ¦ Student Charge Viewing & Management • Bullet B01–B14 R3 Fee ¦ Outstanding Fee Integration with R9 • Bullet B01–B09 R3 Fee ¦ Fee Integration with R4 • Bullet B01–B07 | • UAT-009 • UAT-021 • UAT-037 | • UAT-D06 • UAT-D09 • UAT-D10
US-041 | Online FAS Application Submission | R4 - Financial Assistance | Howard | • SRC-BACKLOG | Product Backlog row 46; R4 ¦ FAS Application Submission • Submission Methods: B01–B02 • Online Application: B01–B03 • Common Application Data & Processing: B01–B09 | • UAT-008 • UAT-028 • UAT-045 • UAT-047 • UAT-049 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-042 | Paper FAS Application Entry | R4 - Financial Assistance | Chan | • SRC-BACKLOG | Product Backlog row 47; R4 ¦ FAS Application Submission • Submission Methods: B01–B02 • Paper Application: B01–B03 • Common Application Data & Processing: B01–B09 | • UAT-029 • UAT-046 • UAT-049 | • UAT-D04 • UAT-D06 • UAT-D09
US-043 | Paper Form Scan & Simulated OCR Prefill | R4 - Financial Assistance | Chan | • SRC-BACKLOG | Product Backlog row 48; R4 ¦ FAS Application Submission • Paper Application: B03–B04 • Common Application Data & Processing: B09 | • UAT-030 • UAT-046 | • UAT-D04 • UAT-D06 • UAT-D09
US-044 | MOEFAS Scheme Lifecycle & Sample Setup | R4 - Financial Assistance | Kent | • SRC-BACKLOG | Product Backlog row 49; R4 ¦ FAS Scheme Management • Bullet B01–B07 R4 ¦ MOEFAS Eligibility Configuration • Bullet B01 R4 ¦ Ví dụ Subsidy Matrix • MOEFAS – Government Financial Assistance 2026: B01–B13 | • UAT-031 • UAT-048 | • UAT-D04 • UAT-D09
US-045 | SBFAS Schemes & Eligibility Descriptions | R4 - Financial Assistance | Kent | • SRC-BACKLOG | Product Backlog row 50; R4 ¦ FAS Scheme Management • Bullet B01–B07 R4 ¦ SBFAS Eligibility • Bullet B01–B06 R4 ¦ SBFAS Manual Review & Decision • Bullet B01–B06 R4 ¦ Ví dụ Subsidy Matrix • SBFAS – High Support: B01–B21 • SBFAS – Medium Support: B01–B20 • SBFAS – Basic Support: B01–B21 | • UAT-031 • UAT-035 | • UAT-D04 • UAT-D06
US-046 | MOEFAS Eligibility Criteria Configuration | R4 - Financial Assistance | Gavin | • SRC-BACKLOG | Product Backlog row 51; R4 ¦ MOEFAS Eligibility Configuration • Bullet B01–B11 R4 ¦ Ví dụ Subsidy Matrix • MOEFAS – Government Financial Assistance 2026: B01 | • UAT-032 | • UAT-D04 • UAT-D06
US-047 | Stage-by-Component Subsidy Matrix | R4 - Financial Assistance | Kent | • SRC-BACKLOG | Product Backlog row 52; R3 Fee ¦ Fee Integration with R4 • Bullet B01–B07 R4 ¦ Subsidy Matrix Configuration • Bullet B01–B08 R4 ¦ Ví dụ Subsidy Matrix • MOEFAS – Government Financial Assistance 2026: B01–B13 • SBFAS – High Support: B01–B21 • SBFAS – Medium Support: B01–B20 • SBFAS – Basic Support: B01–B21 | • UAT-033 | • UAT-D06
US-048 | FAS Application Round & Budget Control | R4 - Financial Assistance | Gavin | • SRC-BACKLOG | Product Backlog row 53; R4 ¦ FAS Scheme Management • Bullet B07 R4 ¦ MOEFAS Eligibility Configuration • Bullet B08 R4 ¦ FAS Eligibility Assessment & Grant Processing • Bullet B02, B07 | • UAT-034 | • UAT-D04 • UAT-D05
US-049 | MOEFAS Eligibility Assessment & Auto Grant | R4 - Financial Assistance | Gavin | • SRC-BACKLOG | Product Backlog row 54; R4 ¦ MOEFAS Eligibility Configuration • Bullet B05–B11 R4 ¦ FAS Eligibility Assessment & Grant Processing • Bullet B01–B07 | • UAT-032 • UAT-034 • UAT-046 • UAT-049 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09
US-050 | SBFAS Manual Assessment & Grant Decision | R4 - Financial Assistance | Kent | • SRC-BACKLOG | Product Backlog row 55; R4 ¦ SBFAS Eligibility • Bullet B01–B06 R4 ¦ SBFAS Manual Review & Decision • Bullet B01–B06 R4 ¦ FAS Eligibility Assessment & Grant Processing • Bullet B01–B07 | • UAT-035 • UAT-045 • UAT-046 • UAT-048 • UAT-049 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-051 | Apply Subsidies to Unpaid Student Charges | R4 - Financial Assistance | Gavin | • SRC-BACKLOG | Product Backlog row 56; R3 Fee ¦ Student Charge Viewing & Management • Bullet B10 R3 Fee ¦ Fee Integration with R4 • Bullet B01–B07 R4 ¦ Subsidy Application to Student Charges • Bullet B01–B07 | • UAT-033 • UAT-037 • UAT-045 • UAT-049 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
US-052 | AI SBFAS Recommendation (Advisory Only) | R4 - Financial Assistance | Gavin | • SRC-BACKLOG | Product Backlog row 57; R4 ¦ SBFAS Eligibility • Bullet B02, B06 R4 ¦ SBFAS Manual Review & Decision • Bullet B02, B06 | • UAT-036 | • UAT-D04 • UAT-D06
US-053 | Unified EA Allocation & Safe Gateway Settlement | R9 - Payment | Gavin | • SRC-BACKLOG | Product Backlog row 58; R9 ¦ Payment Flow & Gateway Integration • Bullet B01–B13 | • UAT-012 • UAT-045 | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10
R6-01 | MOEFAS and SBFAS budget support | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-038 | • UAT-D05
R6-02 | HQ MOEFAS budget setup | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-038 | • UAT-D05
R6-03 | School SBFAS budget setup | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-038 | • UAT-D05
R6-04 | Save/view configured budget | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-038 | • UAT-D05
R6-05 | MOEFAS granted statistics | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-039 | • UAT-D05
R6-06 | Own-school SBFAS statistics | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-039 | • UAT-D05
R6-07 | Total granted subsidy by permitted FAS type | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-039 | • UAT-D05
R6-08 | Budget utilization | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-040 | • UAT-D05
R6-09 | Role-scoped statistics | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-039 | • UAT-D05
R6-10 | Remaining budget | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-040 | • UAT-D05
R6-11 | Exhausted-budget warning and agreed grant behavior | R6 - Budget and statistics | Gavin | • SRC-FS | R6 v0.1, section 2 Confirmed Requirements (draft status retained), plus sections 3 and 4 | • UAT-040 | • UAT-D05
ADD-VIEW-AS | Function 7 View As mode | User-confirmed addition | Chan | • SRC-USER | Current conversation scope correction; local coverage label, not official user-story ID | • UAT-041 • UAT-042 | • UAT-D07 • UAT-D09
ADD-FAQ | Simple system-use FAQ chatbot | User-confirmed addition | Howard | • SRC-USER | Current conversation scope correction; local coverage label, not official user-story ID | • UAT-043 • UAT-044 | • UAT-D08

## Scenarios
ID | Title | Journey | Owner | Support | Role | Coverage Ids | Source references | Fixture IDs | Preconditions | Expected result | Evidence required | Decision IDs | Readiness | Status | Actual result | Evidence | Defects | Executed by | Executed at | Build
UAT-001 | Provision eligible education accounts without duplicates | Lifecycle and parent access | Josh |  | HQ / system | • US-001 | • SRC-BACKLOG • SRC-R1 | • DATA-ROLES • DATA-LIFE | • Authorized isolated initial-sync trigger and agreed identity contract; fresh fixture partition. | • One correct EA per eligible citizen; school enrolment is not an account-creation prerequisite. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-002 | Run the daily newly-seven provision and repeat safely | Lifecycle and parent access | Josh |  | System / HQ observer | • US-002 | • SRC-BACKLOG • SRC-R1 | • DATA-LIFE | • Owned controllable business date; existing student with changed government address. | • Record the clock and scheduler evidence; do not substitute parent login for a scheduled-job demonstration. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-003 | Close an eligible account before viewing or financial activity | Lifecycle and parent access | Josh | • Howard • Gavin | Parent / HQ | • US-003 | • SRC-BACKLOG • SRC-R1 | • DATA-LIFE • DATA-ROLES • DATA-PAY • DATA-TOPUP | • UAT-D03 resolves age/citizenship/positive-balance behavior and current build trigger. Use independent reset copies for each financial action. | • Student profile state is not used as a substitute for EA state. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-004 | Settle residual funds to the CPF simulator exactly once | Lifecycle settlement | Josh |  | System / HQ observer | • US-004 | • SRC-BACKLOG • SRC-R1 • SRC-S2 | • DATA-LIFE | • Current CPF mock contract, identity mapping, allowed trigger and failure/query controls supplied; UAT-D03 resolved. | • No real CPF integration claim; retain success and failure as separately reset variants. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-005 | Parent signs in and sees only verified children | Parent access | Howard | • Chan | Parent A / Parent B | • US-005 | • SRC-BACKLOG • SRC-R1 | • DATA-ROLES • DATA-LIFE | • Named Singpass/government mock and relationship data; account lifecycle fixture prepared by Josh. | • Capture an unsuccessful authentication variant separately; no logged-in identity is fabricated by the test. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. |  | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-006 | Parent reads correct balances, enrolment and filtered history | Parent access | Howard | • Josh • Chan | Parent | • US-006 • US-007 • US-008 | • SRC-BACKLOG • SRC-R1 | • DATA-ROLES • DATA-SCHOOL • DATA-LIFE • DATA-TOPUP | • Two linked children with distinct school/balance/history; Josh and Chan supply before-state receipts. | • Compare values, not screen navigation alone. Include Closed/no-EA display as agreed with lifecycle owner. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-007 | Parent updates permitted contact fields without changing identity | Parent profile | Howard |  | Parent | • US-009 | • SRC-BACKLOG | • DATA-ROLES | • Editable-field list confirmed against delivered parent specification; synthetic contact values only. | • Record exact editable fields and invalid-input variant from existing functional cases. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. |  | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-008 | Parent sees the correct grant decision and application details | FAS result to parent | Howard | • Gavin • Kent | Parent | • US-010 • US-041 | • SRC-BACKLOG • SRC-TRANSCRIPT | • DATA-ROLES • DATA-FAS • DATA-SCHEME | • Kent/Gavin supply approved/rejected/pending applications and result receipts. | • Missing grant display stays an in-scope blocker, not an optional story. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-009 | Show the correct outstanding charges before checkout | Charge to payment | Gavin | • Kent • Howard | Parent | • US-011 • US-040 | • SRC-BACKLOG | • DATA-ROLES • DATA-FEES • DATA-PAY | • Kent provides posted supported/unsupported charge IDs and amounts; parent-child access verified. | • Document charge-to-invoice links for the end-to-end handoff. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-010 | Pay fees from EA funds and retain a correct receipt | Charge to payment | Gavin | • Howard | Parent | • US-012 • US-015 | • SRC-BACKLOG • SRC-R1 | • DATA-PAY • DATA-ROLES | • Independent invoice 100, EA 150; no other pending attempt. | • Insufficient or ineligible account cannot be treated as successful EA payment. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-011 | Pay online in the sandbox and handle cancel/failure | Charge to payment | Gavin |  | Parent | • US-013 • US-015 | • SRC-BACKLOG | • DATA-PAY | • Gateway outcome controls/query available; independent invoices for success and cancel/failure. | • Label sandbox output; do not imply live payment integration. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-012 | Settle a split payment safely, including uncertain outcomes | Charge to payment | Gavin |  | Parent | • US-014 • US-053 | • SRC-BACKLOG | • DATA-PAY | • Agreed reservation/commit/reversal contract and outcome query; separate invoices for success, definitive failure and ambiguous timeout. | • Retain before/after financial records, reservation/reversal links and gateway outcome. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-013 | Create and deactivate school master data without losing history | School administration | Chan |  | HQ / School user | • US-016 | • SRC-BACKLOG | • DATA-ROLES • DATA-SCHOOL | • Delivered master-data actions and synthetic unique school code. | • Use the source school specification for any code/uniqueness rule. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. |  | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-014 | School user signs in with AAD and receives correct school scope | School access | Chan |  | Admin / School user | • US-017 • US-018 | • SRC-BACKLOG • SRC-TRANSCRIPT | • DATA-ROLES • DATA-SCHOOL | • Named Microsoft/AAD test integration or explicit mock; school assignment and first-login fields mapped. | • Distinguish actual AAD integration from a labelled mock. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-015 | Maintain academic structure, students and EA identity links | School administration | Chan | • Josh | School user | • US-019 • US-020 • US-021 | • SRC-BACKLOG • SRC-R1 | • DATA-SCHOOL • DATA-LIFE | • School user authorized for A; independent SC, PR and international student fixtures. | • Student management remains full UAT scope despite lower demo priority. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. |  | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-016 | Enrol and move a student while preserving history | School administration | Chan |  | School user / HQ observer | • US-022 • US-023 • US-025 | • SRC-BACKLOG • SRC-FS | • DATA-SCHOOL | • Agreed academic effective dates; independent student with known prior placement. | • School progression/effective-date details follow chosen R3 variant; do not invent calendar rules. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-017 | Transfer between schools without losing identity or placement history | School administration | Chan | • Howard • Kent | Authorized sending/receiving school users | • US-024 • US-025 | • SRC-BACKLOG • SRC-FS | • DATA-SCHOOL | • Transfer permissions and effective dates agreed; separate sending/receiving school identities. | • Coordinate before later payment/FAS scenarios; use reset copy if transfer would change shared fixtures. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-018 | Import academic and student data with per-row outcomes | School administration | Chan |  | School user | • US-026 • US-027 | • SRC-BACKLOG • SRC-FS | • DATA-CSV • DATA-SCHOOL | • Approved small CSVs using delivered templates; expected row outcomes documented. | • Capture original file and row-result export; do not claim all-or-nothing unless the selected contract requires it. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-019 | Maintain shared and school fee catalogues with ownership | Fees to charges | Kent |  | HQ / School user | • US-034 • US-035 | • SRC-BACKLOG | • DATA-ROLES • DATA-FEES | • Known shared and school-owned fee/component records. | • Record catalogue ownership and component IDs for scheme/subsidy handoffs. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. |  | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-020 | Apply correct fee rates at effective-date and category boundaries | Fees to charges | Kent |  | HQ / School user | • US-036 | • SRC-BACKLOG • SRC-FS | • DATA-FEES • DATA-SCHOOL | • Agreed stage/category/rate/effective-date rules under UAT-D10. | • Record calculation date separately from system clock; no production rates are invented. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-021 | Preview and publish fees once, then expose correct charges | Fees to charges | Kent | • Gavin • Howard | School user / Parent observer | • US-037 • US-038 • US-039 • US-040 | • SRC-BACKLOG • SRC-FS | • DATA-FEES • DATA-SCHOOL | • Known recipient set, effective date/rates and original amounts calculated independently. | • Hand charge IDs and amount receipt to Gavin; retain invalid preview as separate evidence. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-022 | Credit an individual account after review and confirmation | Top-up to parent history | Josh | • Howard | HQ | • US-028 • US-032 | • SRC-BACKLOG • SRC-F2 • SRC-TRANSCRIPT | • DATA-ROLES • DATA-TOPUP | • UAT-D01 selected search/amount/reason/idempotency contract; reset EA at 10. | • Use top-up, not campaign, in user-facing wording. Money precision and Closed-account regressions remain linked functional checks. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 • UAT-D03 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-023 | Configure a bulk top-up and verify the exact preview set | Bulk top-up | Josh |  | HQ | • US-029 • US-030 | • SRC-BACKLOG • SRC-F2 • SRC-TRANSCRIPT | • DATA-TOPUP • DATA-SCHOOL | • Decision records identify criteria, AND/OR, eligibility date, budget and schooling behavior; expected ID set is written before preview. | • For three eligible accounts forecast is 60. Formula/control support must match chosen contract, not implementation guesswork. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-024 | Execute bulk top-up once and reconcile results | Bulk top-up | Josh |  | HQ | • US-031 • US-032 | • SRC-BACKLOG • SRC-F2 • SRC-DEFECTS • SRC-TRANSCRIPT | • DATA-TOPUP | • Confirmed 3-account preview, each at 10, amount 20; current delivery fixes build blockers. | • A new deliberately authorized distribution is different from retrying the same operation; UAT-D01 must define the distinction. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-025 | Recover a partially failed bulk top-up without re-crediting successes | Bulk top-up recovery | Josh |  | HQ | • US-031 • US-032 | • SRC-BACKLOG • SRC-TRANSCRIPT | • DATA-TOPUP | • Known per-item definitive fault, outcome query and chosen recovery workflow under UAT-D02. | • Unresolved outcome is queried before retry. Record request/run/item linkage and recovery evidence; absent recovery remains a blocker. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 • UAT-D02 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-026 | Schedule a top-up for an agreed future date and time | Scheduled bulk top-up | Josh |  | HQ / system | • US-029 • US-031 | • SRC-BACKLOG • SRC-TRANSCRIPT | • DATA-TOPUP | • UAT-D02 supplies supported scheduling behavior/timezone and safe isolated clock/worker controls. | • Not assumed delivered. If no scheduling capability is supplied, record blocked against the in-scope customer concern rather than replacing it with manual execution. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 • UAT-D02 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-027 | Correct a mistaken individual top-up with preserved history | Top-up correction | Josh |  | Authorized HQ | • US-033 | • SRC-BACKLOG • SRC-F2 | • DATA-TOPUP | • UAT-D01 confirms correction authority, adjustment/reversal method, limits and insufficient-balance behavior. | • Historical To Do/deferred labels do not remove this story from the completeness register. Missing mechanism is a blocker. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D01 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-028 | Parent submits FAS with retrieved identity and declared extra income | Online FAS to review | Howard | • Kent • Gavin | Parent | • US-041 | • SRC-BACKLOG • SRC-TRANSCRIPT • SRC-FS | • DATA-ROLES • DATA-FAS • DATA-SCHEME | • Open application form and verified child; government/mock profile and income known; UAT-D04/UAT-D06 record selected form and calculation rules. | • Customer-requested retrieval is not called AI. Definitive submission result and reopened details are required. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-029 | School enters a paper application including a student without an EA | Paper FAS to review | Chan | • Kent • Gavin | School user | • US-042 | • SRC-BACKLOG • SRC-FS | • DATA-SCHOOL • DATA-FAS • DATA-CSV • DATA-SCHEME | • Open form; authorized school student without EA; duplicate online application control on separate fixture. | • Do not require an EA merely because online submission uses an EA-linked child. Multi-child and cross-school variants are explicit in UAT-049. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-030 | Review and correct OCR-prefilled paper data before submission | Paper FAS to review | Chan | • Gavin | School user | • US-043 | • SRC-BACKLOG • SRC-FS | • DATA-CSV • DATA-FAS • DATA-SCHEME | • Delivered simulated OCR mapping and known imperfect scan; no claim of real OCR accuracy. | • Unsupported scan/failure variant leaves a usable manual-entry route if the agreed contract supplies one. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-031 | Create and activate valid MOEFAS and school SBFAS schemes | Schemes to applications | Kent |  | HQ / School user | • US-044 • US-045 | • SRC-BACKLOG • SRC-FS • SRC-TRANSCRIPT | • DATA-SCHEME • DATA-ROLES | • Current scheme lifecycle and permissions selected under UAT-D04; sample config independently reviewed. | • Do not hardcode old four-phase wizard or assume free-text-only SBFAS criteria when FS variants disagree. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-032 | Evaluate configured nationality, GHI/PCI and school criteria | FAS assessment | Gavin | • Howard | HQ configuration / System assessment | • US-046 • US-049 | • SRC-BACKLOG • SRC-FS | • DATA-FAS • DATA-SCHEME • DATA-SCHOOL | • Chosen logical match, thresholds, effective dates and assessment trigger documented under UAT-D04/UAT-D06. | • If v1.3 form-close/ranking rule is chosen, retain rank/tie-break evidence; explicit confirmation is needed before scoring timing. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-033 | Configure stage/component subsidies and apply the correct capped amount | FAS subsidy to charge | Kent | • Gavin | HQ / School user | • US-047 • US-051 | • SRC-BACKLOG • SRC-FS | • DATA-SCHEME • DATA-FEES | • Gavin independently checks sample arithmetic; due dates/effective periods/rounding contract agreed. | • Percent/fixed inputs are independent fixture proposals; chosen cap and rounding rules are explicit. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-034 | Observe application deadlines and the agreed budget behavior | FAS budget and assessment | Gavin |  | HQ / School user / System | • US-048 • US-049 | • SRC-BACKLOG • SRC-FS | • DATA-SCHEME • DATA-BUDGET • DATA-FAS | • UAT-D04 resolves deadline/decision timing and UAT-D05 resolves warning-only versus budget-blocking grant behavior. | • Record excluded boundary interpretations explicitly until resolved. Feature stays in scope even if the rule is pending. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D05 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-035 | School grants or rejects SBFAS under human control | School FAS review | Kent | • Howard • Gavin | School reviewer / HQ observer | • US-045 • US-050 | • SRC-BACKLOG • SRC-FS | • DATA-ROLES • DATA-FAS • DATA-SCHEME | • Correct school routing and final-decision/role permissions selected under UAT-D04. | • HQ decision controls are not assumed: F4 v1.3 makes HQ read-only for decisions. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-036 | Keep SBFAS recommendations advisory and understandable | School FAS review | Gavin | • Kent | School reviewer | • US-052 | • SRC-BACKLOG • SRC-FS | • DATA-FAS • DATA-SCHEME | • Delivered recommendation method and test inputs known; no ML training or accuracy target invented. | • This existing assistance story is separate from the new FAQ chatbot. Simple FAQ scope does not remove US-052. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-037 | Apply subsidy once and protect paid or unsupported charges | FAS subsidy to charge | Gavin | • Kent • Howard | Authorized FAS operator / Parent | • US-051 • US-040 | • SRC-BACKLOG • SRC-FS | • DATA-SCHEME • DATA-FEES • DATA-PAY | • Net-payable calculation and paid/multiple-grant rules confirmed under UAT-D06. | • This is a handoff scenario, not proof of all component cases. Record all entity IDs through the journey. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D06 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-038 | Set and reopen MOEFAS and school budgets within permissions | Budget and statistics | Gavin |  | HQ / School user | • R6-01 • R6-02 • R6-03 • R6-04 | • SRC-FS | • DATA-BUDGET • DATA-ROLES | • Budget period/edit behavior selected under UAT-D05. | • R6 labels come from the draft requirement register, not invented Sprint story IDs. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D05 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-039 | Reconcile granted subsidy statistics and role-scoped totals | Budget and statistics | Gavin |  | HQ / School user | • R6-05 • R6-06 • R6-07 • R6-09 | • SRC-FS | • DATA-BUDGET • DATA-SCHEME | • Counting basis and period/filter interpretation under UAT-D05; independent grant receipt list. | • Do not count a percentage setting itself as spent funds; confirm actual monetary basis. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D05 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-040 | Track remaining budget and warnings without guessing grant policy | Budget and statistics | Gavin |  | HQ / School user | • R6-08 • R6-10 • R6-11 | • SRC-FS • SRC-BACKLOG | • DATA-BUDGET | • UAT-D05 confirms utilized amount, remaining calculation, negative display and warning thresholds. | • R6 draft says warn, not block; old backlog says budget-constrained grant. Neither is silently declared authoritative. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D05 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-041 | Enter View As and see the selected role/target without mutation | View As | Chan | • Howard • Kent | Authorized HQ viewer | • ADD-VIEW-AS | • SRC-USER • SRC-VIEW | • DATA-VIEW • DATA-ROLES | • UAT-D07 confirms authority/targets and read-only contract; named view context mapped. | • Read-only/banners are draft F7 safety proposal, subject to explicit contract confirmation, not general-purpose impersonation. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D07 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-042 | View As blocks writes and exits without contaminating sessions | View As safety | Chan | • Josh • Kent • Howard • Gavin | HQ viewer / target observer | • ADD-VIEW-AS | • SRC-USER • SRC-VIEW | • DATA-VIEW • DATA-PAY • DATA-FAS | • Approved non-destructive QA probes; API-level write enforcement verification by authorized technical tester complements business UI. | • Every module owner supplies own before/after invariants; no destructive probe on live target data. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D07 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-043 | FAQ answers explain how to use the delivered system | FAQ help | Howard | • Kent • Gavin • Chan | Supported system user | • ADD-FAQ | • SRC-USER | • DATA-FAQ | • UAT-D08 records approved answer bank/revision, help location and supported user/language scope. | • FAQ is simple guidance; no LLM/model/provider, accuracy percentage or conversational engine required. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D08 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-044 | FAQ does not look up private data or perform user actions | FAQ help safety | Howard |  | Supported system user | • ADD-FAQ | • SRC-USER | • DATA-FAQ • DATA-ROLES | • Known generic answer bank; record balances/application/payment before-state. | • Security checks are proportionate to actual simple implementation; no unsupported claim that a generative model exists. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D08 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-045 | Rehearse online FAS through school review, subsidy and payment | Integrated FAS journey | Howard | • Kent • Chan • Gavin | Parent -> School/System -> Parent | • US-041 • US-050 • US-051 • US-010 • US-011 • US-014 • US-015 • US-053 | • SRC-BACKLOG • SRC-FS • SRC-TRANSCRIPT | • DATA-ROLES • DATA-SCHOOL • DATA-FAS • DATA-SCHEME • DATA-FEES • DATA-PAY | • Component owners have current-build readiness evidence; one linked child/charge used throughout; all listed decisions resolved for this route. | • Each owner signs off their handoff evidence. QA rehearsal is not business acceptance. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D05 • UAT-D06 • UAT-D09 • UAT-D10 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-046 | Rehearse paper application through assessment and parent result | Integrated paper FAS journey | Chan | • Kent • Gavin • Howard | School -> System/School -> Parent where authorized | • US-042 • US-043 • US-049 • US-050 • US-010 | • SRC-BACKLOG • SRC-FS | • DATA-CSV • DATA-FAS • DATA-SCHEME • DATA-SCHOOL • DATA-ROLES | • Known paper identity and any parent linkage; chosen MOEFAS/SBFAS routing/timing contract. No-EA branch has separately agreed result visibility. | • Record no-EA paper flow and linked-parent visibility as distinct variants. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-047 | Handle FAS retrieval, document and submission failures visibly | Online FAS recovery | Howard | • Chan | Parent | • US-041 | • SRC-BACKLOG • SRC-FS • SRC-TRANSCRIPT | • DATA-ROLES • DATA-FAS • DATA-SCHEME | • Agreed government retrieval outage, document validation and submission-outcome controls; separate reset copy per failure variant. | • Record draft-retention and exact retry behavior under UAT-D06 before scoring; test does not invent new document limits or retry routes. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-048 | Preserve normal role boundaries across financial and FAS actions | Cross-function access safety | Chan | • Josh • Kent • Gavin | Parent / School / HQ negative controls | • US-017 • US-028 • US-044 • US-050 | • SRC-BACKLOG • SRC-FS | • DATA-ROLES • DATA-TOPUP • DATA-FAS • DATA-SCHEME | • Approved isolated technical controls complement visible menus; BA has confirmed ordinary and View As role rights separately. | • Do not infer access correctness solely from disabled buttons. Retain before/after state; no new production permission change is authorized. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run
UAT-049 | Submit a family application for two children with independent outcomes | Family FAS submission and school routing | Howard | • Chan • Kent • Gavin | Parent, then paper-entry School user on a separate reset copy | • US-041 • US-042 • US-049 • US-050 • US-051 • US-010 | • SRC-BACKLOG • SRC-FS | • DATA-ROLES • DATA-FAS • DATA-SCHOOL • DATA-SCHEME • DATA-FEES | • Use two eligible applying siblings with one shared household. Execute online and paper variants separately; baseline siblings at School A. UAT-D04 records cross-school sibling submission/routing permissions before the School A/B variant is scored. • Map one family ID, two child IDs, two application IDs and separate child charge IDs. Income/member inclusion follows UAT-D06. F10 section1.2/BR4-BR5 and F5 section2/BR1-BR2 are the source locators. | • Keep two source-specific execution variants and per-child before/after evidence. Family grouping is not one shared acceptance decision. Same-school baseline is mandatory; cross-school variant remains an explicit UAT-D04 contract gate. | • Record approved build/URL, environment/mock versions, business date, operator and effective role. • Keep input IDs, user-visible result and authoritative before/after records; mask identifiers in shared evidence. • Link exact action/step to result, defect or pending-rule record; record reset verification separately. | • UAT-D04 • UAT-D06 • UAT-D09 | Pending named build, fixture mapping and referenced behaviour decisions; not execution evidence. | Not Run

## Script steps
Scenario ID | Step | Action | Observable expected
UAT-001 | 1 | Run initial synchronization for the known citizen set. | Only eligible valid SC records aged 7 to below 16 receive one EA linked to the correct student.
UAT-001 | 2 | Compare age/noncitizen/missing optional-parent controls. | Ineligible records do not get EAs; absent parent NRIC alone does not reject an otherwise valid citizen.
UAT-001 | 3 | Rerun the agreed provisioning flow and inspect identities/balances. | No duplicate EA, no opening money movement; new accounts Active with SGD 0.00 under R1 draft.
UAT-002 | 1 | Advance to the recorded seventh birthday and invoke the delivered daily trigger. | Newly-seven eligible citizen is processed on the agreed date.
UAT-002 | 2 | Inspect the older existing student profile and daily query set. | Daily incremental flow does not refresh all older profiles under R1 v1.2.
UAT-002 | 3 | Repeat the job for the same date. | Exactly one EA remains; no additional financial entry.
UAT-003 | 1 | Access a below-16 citizen control and an exactly-16 zero-balance account. | Control remains Active; eligible account follows agreed closure check and records correct final state.
UAT-003 | 2 | Attempt top-up and payment on closure-eligible accounts, including one whose persisted state was Active. | Eligibility check prevents new ineligible financial activity; no wrong debit/credit.
UAT-003 | 3 | Reopen the Closed account and inspect allowed history. | No duplicate closure; authorized historical viewing remains available; status/date remain consistent.
UAT-004 | 1 | Trigger eligible closure with residual SGD 40. | Transfer follows agreed lifecycle; account and CPF result are linked, with exactly 40 settled on success.
UAT-004 | 2 | Query CPF outcome, EA balance and ledger rather than trusting a success banner. | No lost or duplicated funds; confirmed success and final account state agree.
UAT-004 | 3 | Repeat access and separately test a definitively failed CPF response. | Confirmed transfer is not repeated; failure does not claim settlement or discard the 40.
UAT-005 | 1 | Sign in as Parent A and inspect linked children. | Only verified children are listed; identity source and mock are labelled.
UAT-005 | 2 | Try to reach an unrelated child using the delivered navigation and a known direct link in authorized QA. | Unrelated child information is not exposed.
UAT-005 | 3 | Sign out and sign in as Parent B. | No prior family data/session context is reused.
UAT-006 | 1 | Open each linked child dashboard and school details. | Child identity, EA balance and current school/year/level/class match the fixture and authorized data.
UAT-006 | 2 | Open history and use supported date/type filters, including a filter with no matches. | Correct matching movements/totals appear; empty result is explicit and does not show another child.
UAT-006 | 3 | Change child and return after the agreed top-up or payment handoff. | Updated balance and history agree with ledger; no stale child context or lost history.
UAT-007 | 1 | Edit one permitted contact field and save. | Valid contact change is saved for the correct parent.
UAT-007 | 2 | Reopen profile after a new login. | Persisted allowed value is retained according to agreed government/local precedence.
UAT-007 | 3 | Attempt to edit government identity through available controls. | Identity remains protected; unrelated family profile is unchanged.
UAT-008 | 1 | Open the submitted application and its details. | Previously submitted identity, income, documents and child remain accessible to the authorized parent.
UAT-008 | 2 | Inspect pending, granted and rejected examples. | Displayed scheme/child/result/reason reflect actual assessment; pending is not falsely shown as approved.
UAT-008 | 3 | Compare a grant with the affected charge and another family. | Grant and payable result reconcile; other-family application cannot be viewed.
UAT-009 | 1 | Open outstanding fees for a linked child. | Correct school, period, component, original/subsidy/net amount and current state appear.
UAT-009 | 2 | Select the permitted charges and review the invoice. | Invoice items and total match eligible outstanding charges; no other child/school mixing.
UAT-009 | 3 | Return to a paid or canceled control. | Paid charges are not offered again; canceled/unpaid treatment follows the agreed state contract.
UAT-010 | 1 | Review and confirm EA-only payment for 100. | Review shows correct source and amount before consent.
UAT-010 | 2 | Read payment outcome, EA balance and charge/invoice state. | One successful payment of 100; EA closes at 50; invoice/charges are settled once.
UAT-010 | 3 | Open receipt/history and revisit the payment. | Receipt reference/items total 100; no second debit or duplicate settlement.
UAT-011 | 1 | Complete an online-only sandbox payment of 100. | Correct invoice/amount is sent to the named sandbox; no EA money is used.
UAT-011 | 2 | Read receipt, settlement and charge status. | One confirmed success for 100; receipt and invoice agree.
UAT-011 | 3 | On a reset invoice cancel or cause a definitive gateway failure. | No paid receipt or settled invoice is fabricated; EA unchanged and charge state follows agreed recovery.
UAT-012 | 1 | Confirm invoice 100 split EA 40 plus online 60. | Breakdown totals 100 and matches parent confirmation.
UAT-012 | 2 | Resolve successful gateway outcome and inspect all records. | Exactly 40 net EA debit and 60 online payment; one settled invoice, EA closes at 0.
UAT-012 | 3 | Run failure and timeout variants on reset data; query outcome before any retry. | Definitive failure leaves no net EA debit or paid invoice. Unknown outcome remains unresolved until queried, with no blind duplicate attempt.
UAT-012 | 4 | Replay a known settled notification or revisit success. | No additional debit, credit, invoice settlement or receipt duplication.
UAT-013 | 1 | Create School A and reopen its details. | Unique code/name/type and offered structure persist correctly.
UAT-013 | 2 | Update permitted details and view related records. | Correct school changes; linked historical student/charge records remain identifiable.
UAT-013 | 3 | Deactivate a separate historical school and inspect authorized access. | Historical records are retained and access follows agreed inactive-school behavior, without cross-school leakage.
UAT-014 | 1 | Assign a test school user through the delivered authorized setup. | User is linked to intended School A; no admin-created password workflow replaces AAD.
UAT-014 | 2 | Sign in through AAD and complete permitted first-login information. | User lands in correct role/school context and permitted profile persists.
UAT-014 | 3 | Attempt another school context and compare a user with no assignment. | School B data is protected; unassigned user cannot silently inherit a school.
UAT-015 | 1 | Create current-year levels/classes and add/update student records. | Configured structure and allowed student details persist within school scope.
UAT-015 | 2 | Link an SC student to the existing matching EA. | One correct identity link; no duplicate or unrelated EA association.
UAT-015 | 3 | Save a valid PR/no-EA student and inspect identity mismatch control. | No-EA record stays valid; mismatch is not silently linked or rejected merely for lacking EA.
UAT-016 | 1 | Assign student to a configured class and inspect current enrolment. | Correct school/year/level/class and active placement are shown.
UAT-016 | 2 | Move class/level/year using the agreed effective date. | Current placement changes at the correct boundary; prior placement is preserved.
UAT-016 | 3 | Inspect current/history as School A and HQ, then as School B. | Permitted history is complete and ordered; B cannot access A-only records.
UAT-017 | 1 | Record transfer out of A and transfer into B with authorized actors. | Correct student and effective dates are used; neither actor receives unauthorized school privileges.
UAT-017 | 2 | Inspect school-specific IDs, current placement and previous enrolment. | Receiving-school identity is correct and history retained without duplicate current placement.
UAT-017 | 3 | View parent details and a later fee preview. | Authorized enrolment display and future recipients reflect transfer date, without overwriting prior charges.
UAT-018 | 1 | Preview academic structure CSV containing valid/invalid references. | Rows, validation issues and intended changes are visible before commit.
UAT-018 | 2 | Import student CSV including optional empty class, duplicate and invalid reference. | Accepted/rejected rows follow agreed contract and identify row-specific outcomes; no cross-school insertion.
UAT-018 | 3 | Reconcile lists, enrolments and row totals, then retry only as permitted. | Every row accounted for; no unexplained partial creation or silent duplicate on retry.
UAT-019 | 1 | Create/update shared type/components as HQ. | Allowed shared definitions persist and are visible in permitted school workflows.
UAT-019 | 2 | Create school-specific fee/component and permitted extension as School A. | A local values do not overwrite shared definitions or B catalogue.
UAT-019 | 3 | Deactivate a historical component and attempt unauthorized edit. | Billing history remains intact; unauthorized/shared edits are prevented.
UAT-020 | 1 | Configure known category/stage rates for adjacent valid periods. | Configuration persists with intended ownership and date ranges.
UAT-020 | 2 | Preview just before/on the change date for SC and PR controls. | Independent expected rate selected for each category/stage/date, with no ambiguous overlap.
UAT-020 | 3 | Try an invalid overlap or missing applicable rate. | No silently wrong charge; delivered validation/exception follows agreed rule.
UAT-021 | 1 | Configure publication period/targets/components and preview. | Exact expected recipients, component amounts and total shown; preview creates no billable charges.
UAT-021 | 2 | Resolve a missing-rate control and publish the valid publication. | Only intended eligible charges become billable with correct source links; generation does not depend on FAS.
UAT-021 | 3 | Repeat the agreed publish action and inspect Admin/Parent views. | No duplicate billing; both views agree on issued charge state and amounts.
UAT-022 | 1 | Search exact intended account, enter top-up 20 and reason, then review. | Correct recipient, current 10, amount 20 and projected 30 are visible before consent.
UAT-022 | 2 | Cancel once and inspect balance; then confirm a fresh valid attempt. | Cancel changes nothing; confirmed success creates exactly one 20 credit and balance 30.
UAT-022 | 3 | Inspect HQ history and parent history; query/retry the same known result per contract. | One attributable movement and matching balance; no duplicate credit on replay.
UAT-023 | 1 | Configure chosen age/balance/enrolment criteria and per-account 20. | Saved values reopen exactly as configured; criteria meaning is explicit.
UAT-023 | 2 | Preview boundary/multiple-match/ineligible controls. | Returned ID set, exclusion reasons, count and forecast match agreed rules; no duplicates or ledger movements.
UAT-023 | 3 | Change criteria/amount and cancel confirmation. | Obsolete preview cannot authorize an unintended run; cancellation changes no balance.
UAT-024 | 1 | Review current recipients/total and confirm the run. | Explicit consent relates to this definition and forecast, with no accidental execution.
UAT-024 | 2 | Read completed result and independent balances/items. | Three successful items, total 60; each balance 30; individual movements and run totals reconcile.
UAT-024 | 3 | Cancel a repeat prompt and exercise same-request replay separately. | Cancel adds nothing; replay follows agreed one-run/repeat policy without unintended extra credit.
UAT-025 | 1 | Execute 3-account top-up with one controlled definitive failure. | Two successes credit 40; failed account stays at 10 and has an identifiable result/reason.
UAT-025 | 2 | Inspect results and select the agreed failed-record recovery. | Recovery uses actual failed outcomes, not a fresh broad profile rule or 20 separate manual credits.
UAT-025 | 3 | Clear the fault, retry and compare all balances/references. | Only failed account receives 20; each closes at 30, total intended distribution 60, prior successes unchanged.
UAT-026 | 1 | Save a future top-up and reopen its schedule. | Exact agreed local date/time/timezone retained; no immediate credit.
UAT-026 | 2 | Inspect before due time, then advance the approved business clock/trigger. | No early distribution; due execution follows chosen timing and eligibility policy.
UAT-026 | 3 | Inspect run/history and repeat worker wake-up after completion. | One intended distribution with attributable scheduled trigger; no duplicate credit.
UAT-027 | 1 | Create a known mistaken top-up of 20 on opening 10. | Original credit and resulting 30 are attributable and retained.
UAT-027 | 2 | Apply the agreed authorized full correction with reason. | Compensating outcome restores intended 10 and links to the original; no destructive history rewrite.
UAT-027 | 3 | Inspect history and repeat the same correction request. | Original/correction entries reconcile; no repeated debit or unsupported negative balance.
UAT-028 | 1 | Open application and identify parent/child using agreed NRIC/retrieval flow. | Required government details retrieved, no unnecessary manual gender/race/phone fields required for this application.
UAT-028 | 2 | Declare additional income 400, attach synthetic support and review household inputs. | Declaration/document visible; agreed fixture calculation displays GHI 2400 and PCI 600 if chosen membership/inclusion rules apply.
UAT-028 | 3 | Submit and reopen the same application as parent and authorized reviewer. | One complete application; reviewer sees exactly the submitted values/documents; no premature grant or unrelated-family access.
UAT-029 | 1 | Enter paper application with school/student/household data and attach scan. | No-EA student is handled per agreed paper eligibility. A control with no child at the submitting school is blocked; cross-school siblings follow UAT-D04 rather than a blanket selection ban.
UAT-029 | 2 | Review/save/submit, then open reviewer details. | Correct paper provenance, document and application data retained in common review flow.
UAT-029 | 3 | Attempt a known duplicate online/paper application under agreed duplicate rule. | No silent duplicate assessment/grant; user receives actionable outcome.
UAT-030 | 1 | Upload known paper sample to OCR/prefill. | Supported fields prefilled and source remains identifiable; no automatic submission or grant.
UAT-030 | 2 | Compare to paper and correct the deliberately wrong income/identity field. | Operator can review/correct values and validation runs on corrected data.
UAT-030 | 3 | Submit and reopen reviewer details. | Only confirmed corrected data reaches assessment; scan retained and simulator labelled.
UAT-031 | 1 | Create/save/reopen MOEFAS as HQ and SBFAS as School A. | Correct owner, valid timeline and configured subsidy/eligibility retained; no B-school editing.
UAT-031 | 2 | Review and publish valid scheme, plus an invalid timeline control. | Valid scheme available at intended time; invalid configuration is not silently active.
UAT-031 | 3 | Inspect form-open/close and effective-date boundary states. | Application availability and subsidy eligibility use their distinct agreed dates, not just a UI wizard label.
UAT-032 | 1 | Configure known criteria and record independent expected outcomes for GHI-only, PCI-only, neither and exact-boundary households. | Expected table includes nationality/school gates; no guessed production thresholds.
UAT-032 | 2 | Submit these applications and inspect before/after the agreed trigger. | Waiting and assessed states follow selected lifecycle, not a presumed immediate grant.
UAT-032 | 3 | Compare each result, recorded inputs and reason to expected table. | Each result reproducible from agreed rules; wrong-school/nationality controls cannot bypass gates.
UAT-033 | 1 | Configure 50% support for component 80 on original charge 100. | Correct stage/component support saved; unsupported component 20 has no subsidy.
UAT-033 | 2 | Apply an eligible grant and inspect original/subsidy/net values. | Original 100 unchanged, subsidy 40, net 60 on the intended unpaid charge.
UAT-033 | 3 | On a reset variant apply fixed 100 support capped at supported 80. | Subsidy 80, net total 20; no negative payable, and another stage/component is unchanged.
UAT-034 | 1 | Submit before/on/after the agreed application cutoff using isolated date controls. | Acceptance/rejection of submission matches recorded timezone/cutoff; effective period remains separate.
UAT-034 | 2 | Assess applications with sufficient, exact and insufficient budget on reset copies. | Grant/warning/block and resulting balances follow the chosen rule, not whichever draft is convenient.
UAT-034 | 3 | Reopen budget, assessment history and repeated trigger result. | Totals and decision provenance reconcile; no duplicate grant or silent budget commitment.
UAT-035 | 1 | Open eligible school review application and inspect submitted details/support. | Only authorized school application is actionable; inputs match parent/paper submission.
UAT-035 | 2 | Grant selected school scheme on one fixture and reject with reason on another. | Human decision, scheme and reason retained; MOEFAS not-eligible alone is not mislabeled final FAS rejection.
UAT-035 | 3 | Reopen as reviewer/HQ/parent and try a prohibited redecision or wrong-school action. | Finality/permissions follow chosen contract; views agree and no unauthorized grant occurs.
UAT-036 | 1 | Open an application with known eligible schemes and view any recommendation. | Suggestion is identifiable as advisory; source/input and selected suggestion are inspectable under agreed behavior.
UAT-036 | 2 | Choose a different permitted scheme or reject manually. | Authorized human decision prevails, with no auto-grant by the recommendation.
UAT-036 | 3 | Test unavailable/no-match recommendation on separate fixture. | Application and manual decision remain usable under agreed fallback; no false scheme or invented eligibility.
UAT-037 | 1 | Apply known grant to eligible unpaid charge 100 and inspect net 60. | Correct supported subsidy 40 applied, original retained, invoice reflects payable 60.
UAT-037 | 2 | Repeat grant/application trigger and compare a paid/unsupported/date-ineligible control. | No duplicate reduction; controls change only if an explicitly agreed adjustment rule permits it.
UAT-037 | 3 | Pay the net charge and reconcile grant, charge, invoice, receipt and EA/gateway records. | Parent pays 60 once, subsidy remains 40, original 100; no hidden double subsidy/debit.
UAT-038 | 1 | Set MOEFAS budget 1000 as authorized HQ. | Correct type/period budget persists and reopens as 1000.
UAT-038 | 2 | Set independent School A/B SBFAS budgets as permitted school users. | Each amount belongs to intended school and period.
UAT-038 | 3 | Attempt cross-school or unauthorized budget access/edit. | No disclosure/change outside permissions; original budgets unchanged.
UAT-039 | 1 | View MOEFAS and School A SBFAS granted statistics. | Correct FAS type, authorized school and period displayed.
UAT-039 | 2 | Compare totals with two counted grants 40 and 60. | Total 100 under agreed definition; no pending/rejected/other-school amount included.
UAT-039 | 3 | Change filters/school role and repeat the same query. | Totals stable/reproducible for selected scope; no cross-school leakage or duplicate counting.
UAT-040 | 1 | Open configured 1000 budget with counted use 100. | Used 100 and remaining 900 under agreed basis, tied to same scope/period.
UAT-040 | 2 | On reset boundary fixtures reach and exceed available budget. | Warnings/remaining presentation follow agreed policy; no hidden count or accidental corruption.
UAT-040 | 3 | Assess another valid application and inspect grant outcome and statistics. | Warning-only or blocking behavior matches recorded decision; accounting and displayed totals remain consistent.
UAT-041 | 1 | Enter View As for School A and inspect identity/banner. | Mode and target visibly identified; viewer does not silently become a real School A actor.
UAT-041 | 2 | Compare permitted school screen data with same target baseline. | Displayed data and actions reflect chosen target scope without unauthorized HQ data.
UAT-041 | 3 | Repeat for permitted Parent A and attempt a prohibited target. | Correct family view; unauthorized target denied without leaking its data.
UAT-042 | 1 | In View As try profile save, FAS submission/decision, fee publish, payment and top-up using available controls. | Read-only proposal prevents every mutation; capture before/after records, not just disabled button screenshots.
UAT-042 | 2 | Have authorized tester attempt corresponding write requests with View As context in isolated QA. | Server enforces agreed read-only boundary and preserves balances, records and permissions.
UAT-042 | 3 | Exit View As, reopen original context and inspect real target session/audit. | Original actor restored; no stale target access; real user session unaffected per chosen contract; audit distinguishes viewer and target.
UAT-043 | 1 | Ask the agreed sign-in, balance/history, payment and FAS how-to questions. | Answer facts and navigation match the delivered UI and approved answer bank.
UAT-043 | 2 | Ask paraphrases and follow the instructions in a separate normal user session. | User can find the described screen/action; no invented buttons, policy or eligibility promises.
UAT-043 | 3 | Ask an unknown/out-of-scope question. | Defined honest fallback/support route, not an invented answer.
UAT-044 | 1 | Ask for another parent balance or a personal payment status. | FAQ does not retrieve/disclose private records; may explain how the authorized user can view them normally.
UAT-044 | 2 | Ask the chatbot to pay, top up, submit FAS or alter profile. | No state change, transaction, hidden auto-fill or approval; only safe how-to guidance/fallback.
UAT-044 | 3 | Send an instruction to ignore help limits and invent an official assistance rule. | No claim of authoritative decision or private action; answer remains within documented system-use help.
UAT-045 | 1 | Parent submits known complete application; reviewer opens same application ID. | Identity, income, document and child agree across portals; correct school/system reviewer receives it.
UAT-045 | 2 | Run agreed assessment/review and apply 40 subsidy to original 100 charge. | Attributable decision, original 100, subsidy 40, net 60; parent result and fee view agree.
UAT-045 | 3 | Parent pays net 60 using independent EA 40 plus online 20 allocation. | One invoice settled, EA net debit 40 and gateway 20; receipt total 60 and history agree.
UAT-045 | 4 | Reopen parent/admin/grant/budget views and compare entity links. | All views reconcile, no duplicate grant/payment, authorized scope preserved; budget follows chosen accounting.
UAT-046 | 1 | School scans/types and confirms corrected application. | One paper application with correct provenance/household/support reaches review.
UAT-046 | 2 | Run the selected assessment trigger and school-decision branch on independent data. | Correct route and final or pending result, with no OCR auto-grant or unauthorized HQ decision.
UAT-046 | 3 | Inspect review/audit and authorized parent result for the linked-child branch. | Same decision/details appear; no assumption that a no-EA unlinked parent can access a portal result.
UAT-047 | 1 | Open the application with government retrieval unavailable, then restore the controlled dependency. | No invented identity/income or silent use of another family record; failure/recovery follows the selected contract.
UAT-047 | 2 | Declare extra income without required support, then try an invalid upload and a valid synthetic document. | Agreed required/type/size validation is visible; no silent loss or fabricated successful upload. Valid corrected data can be reviewed.
UAT-047 | 3 | Interrupt submission, query the application outcome and retry only as permitted. | Clear unresolved/saved/submitted state; no duplicate application or premature assessment; reopened details retain confirmed values.
UAT-048 | 1 | As Parent and School user, try the HQ top-up action through delivered entry points. | No unauthorized credit, balance change or sensitive recipient disclosure, regardless of hidden menu.
UAT-048 | 2 | As School A user, try School B scheme/application decision via known QA fixture links and authorized request probes. | B data is protected and no scheme or grant changes.
UAT-048 | 3 | As HQ inspect permitted MOEFAS configuration and attempt a school decision according to chosen F4 role rule. | Only authorized operations succeed; decision actor/audit and unchanged negative-control records are verified.
UAT-049 | 1 | Select both verified siblings, enter/retrieve shared household inputs once, review and submit the family online application. | Exactly two different child application IDs share one family ID. Both carry the same confirmed household inputs; household count includes each person once, not two copies of shared adults or applying children.
UAT-049 | 2 | Open both child applications and the parent family summary. | Correct child, school, form/scheme route and charge links are retained separately, with shared context/documents handled under the confirmed contract; no merged or overwritten child result.
UAT-049 | 3 | On a separate reset copy enter the same two-child family through paper submission, then repeat with one child at A and one at B after UAT-D04 is resolved. | Paper submission also produces one application per child with shared family identity and Paper provenance. Baseline and cross-school selection/routing follow the chosen rule; if cross-school behavior is unresolved this variant stays blocked, not automatically forbidden.
UAT-049 | 4 | Have the authorized reviewer/system decide Child A while Child B remains pending; inspect both, then apply the documented independent decision to B. | A decision does not propagate to B. Each application records its own authorized reviewer, scheme, result/reason and effective date; any school review is routed to that child school under UAT-D04.
UAT-049 | 5 | Inspect each parent result, child charge and grant/subsidy record, and a paper control with no child at the submitting school. | Each result and subsidy belongs only to its child/charge, with no household-wide double grant or accidental subsidy to pending/rejected sibling. The no-child-at-school control is rejected under the selected F5 rule, without silently rejecting a permitted sibling variant.

## Data
ID | Owner | Description | Setup | Expected result | Reset | Standing
DATA-ROLES | Chan | Named HQ operator, School A operator, School B operator, Parent A with two children, unrelated Parent B and an unauthorized role. | Map logical users to approved QA users without recording credentials. Include AAD/Singpass mocks with named contracts; record operator and effective role separately. | School A and Parent A cannot access B records; real and simulated actor remain distinguishable. | End only owned sessions. Restore role mapping through approved setup. Do not change shared user permissions. | QA synthetic fixture proposal; not provisioned or tested
DATA-LIFE | Josh | Citizens below 7, turning 7, age 10, just below 16, turning 16; PR; existing Active and Closed EA; residual balances 0 and 40. | Set an isolated business date/DOB list, source citizenship, duplicate identity and changed government record. Include one record without parent NRIC and a school student with no EA. | Eligibility uses recorded age and agreed current government contract. No fabricated CPF success; control pending obligations explicitly. | Use approved owned-tenant seed/reset and clock restoration; verify account, ledger and CPF mock state after reset. | QA synthetic fixture proposal; not provisioned or tested
DATA-SCHOOL | Chan | Two schools, current/prior academic years, levels, classes, SC/PR/international students, school-scoped IDs and transfer history. | Create school records independently of EA. Map one SC to an EA, leave one PR student without EA; prepare change and transfer examples. | Current enrolment is unambiguous; history retained; school permissions remain isolated. | Reset only owned school/student/enrolment records, in dependency order, after downstream charges/applications are removed. | QA synthetic fixture proposal; not provisioned or tested
DATA-CSV | Chan | Small academic and student CSVs with valid rows, duplicate rows, invalid reference and optional blank class; paper scan with known OCR mistakes. | Use the delivered CSV templates; retain row numbers, input and expected row outcomes agreed with BA. No real NRIC/documents. | Every import row has a reconciled result; an OCR mistake is corrected before submission. | Restore owned import targets and paper drafts. Do not wipe all school records. | QA synthetic fixture proposal; not provisioned or tested
DATA-FEES | Kent | Known School A/B fee catalogues, stage/category rates, prior/current effective dates and one deliberately missing rate. | For isolated scenarios, create an original charge of SGD 100, supported component 80 plus unsupported component 20. Keep a separate paid charge and a separate due-date boundary charge. | Each generated charge has independently calculated recipient, component and amount. No duplicate billing on replay. | Reset publications, charges, invoices and grants as one owned dependency set; verify outstanding totals before reuse. | QA synthetic fixture proposal; not provisioned or tested
DATA-TOPUP | Josh | Three eligible EAs at SGD 10 each; controlled ineligible boundary accounts; one preselected eligible account can fail definitively. | Use a top-up of SGD 20 per account. Preview expected set is explicit under UAT-D01. A successful clean run yields total SGD 60, balances SGD 30 each. Use a separate reset copy for partial failure. | Partial-failure example: two successes = SGD 40; failed account unchanged at 10. Definitive failed-only retry yields total SGD 60 with successful accounts still at 30. | Restore own batches/items, references and balances atomically through approved reset; do not replay money requests as cleanup. | QA synthetic fixture proposal; not provisioned or tested
DATA-FAS | Gavin | Households that match GHI only, PCI only, neither, threshold boundary; SC/PR; School A/B; documented extra income. Family variant: two parents and two applying siblings, initially both at School A, plus a separate School A/B sibling variant. | Suggested arithmetic fixture: government GHI 2000 plus declared additional income 400, four distinct counted people, including the two applying siblings exactly once. If BA confirms inclusion/count rules, total GHI 2400 and PCI 600. Use synthetic support document. For family submission record one family ID and two different child application IDs; use separate reset copies for online and paper. Add a paper control with neither child at the submitting school. | Shared household inputs/counts are consistent in both child applications; each child keeps its own school, routing, decision and charge links. A decision for one child does not decide or subsidize its sibling. Cross-school paper acceptance follows UAT-D04, never an assumed blanket ban. | Restore owned family/child applications, documents, decisions and grant links; keep evidence before reset. | QA synthetic fixture proposal; not provisioned or tested
DATA-SCHEME | Kent | MOEFAS and School A/B SBFAS schemes; draft/published states; form-open/close and effective-date boundaries; supported/unsupported components. | Suggested subsidy fixtures: 50% of supported SGD 80 is SGD 40, net charge 60; separate fixed subsidy 100 capped at supported 80 gives net total 20. Separate grant/charge data per variant. | Original amount remains 100, unsupported 20 unchanged, no duplicate reduction; configured stage/component mapping drives result. | Reset schemes only after owned grant/charge links are cleared. Restore business clock; do not alter shared policies. | QA synthetic fixture proposal; not provisioned or tested
DATA-BUDGET | Gavin | MOEFAS and each school SBFAS configured budgets with independently counted grants, rejection, pending and other-school records. | Proposed sample: budget 1000 and two counted grants 40 and 60; an ungranted pending/rejected item and School B grant are excluded from A totals. Boundary budgets sufficient/exact/over-used require agreed UAT-D05 accounting. | Under the agreed counting basis, counted total 100, remaining 900. Warning/block behavior is not guessed from old backlog. | Restore owned budget/grant examples and calculation receipts; retain evidence of before/after totals. | QA synthetic fixture proposal; not provisioned or tested
DATA-PAY | Gavin | Independent invoices for EA-only, online-only, split, canceled/failed/timeout, already paid and repeated callbacks. | Use invoice 100 with EA 150 for EA-only; EA 40 + gateway 60 for split. The separate integrated FAS fixture has original charge 100, subsidy 40, net invoice 60, opening EA 40 and gateway portion 20. Gateway sandbox supports success, definitive failure and ambiguous timeout with queryable outcomes. | One settled invoice has one effective payment; canceled/definitively failed attempt has no net debit. Unknown outcome is resolved before retry. | Reset owned invoices, payments, reservations, wallet entries and gateway state together. Verify opening balances and outstanding charge count. | QA synthetic fixture proposal; not provisioned or tested
DATA-VIEW | Chan | Authorized HQ viewer plus School A and Parent A targets and one prohibited target, with known balances/application details. | Use read-only View As proposal. Capture original actor/session, target identity/role, consent/authority if required and before-state for contact/fees/FAS/payments/top-ups. | Clear View As identity; no product mutation under read-only mode; exit restores original context without altering the real user session. | Exit owned View As sessions; compare before/after state and restore via approved setup only. No direct tampering with a real target session. | QA synthetic fixture proposal; not provisioned or tested
DATA-FAQ | Howard | Versioned answer bank checked against delivered UI: sign in, find child balance/history, pay fees, submit/view FAS, contact support. | Agree expected answer facts and navigation with each owner. Include paraphrase, unknown question, personal-balance request and instruction to submit/pay. No personal data, LLM vendor or generation approach assumed. | Answers explain available actions; no personal lookup, invented policy, transaction execution or unrequested FAS autofill. | Clear owned test conversations if storage exists and reset only fake context. Keep expected-answer revision and evidence. | QA synthetic fixture proposal; not provisioned or tested

## Decisions
ID | Topic | Question | Owner | Source references | Affects scenarios | Status | Resolution
UAT-D01 | Top-up contract conflicts | Choose and cite the governing criterion combination/fields, eligibility date, per-run budget, valid repeat-vs-retry policy, and correction contract. Older narrow-plan deferrals do not remove stories. | Josh with BA, Hugh and Kevin | • SRC-F2 • SRC-BACKLOG | • UAT-022 • UAT-023 • UAT-024 • UAT-025 • UAT-026 • UAT-027 | Open
UAT-D02 | Scheduled top-up and failed-record recovery | Record the delivered schedule/timezone/worker behavior and failed-only recovery method requested by the customer, including uncertain outcomes. Do not substitute broad rerun/manual individual credits without customer agreement. | Josh with BA/Dev and business representative | • SRC-TRANSCRIPT • SRC-MOM | • UAT-025 • UAT-026 | Open
UAT-D03 | Lifecycle and CPF settlement | Map requested R1 v1.2 CR/TD/WA rules to current delivered trigger, citizen-change policy, positive balances, pending transactions, Government failure and CPF simulator outcomes. CPF remains in coverage. | Josh with BA and Kevin/Hugh | • SRC-R1 • SRC-S2 • SRC-BACKLOG | • UAT-001 • UAT-002 • UAT-003 • UAT-004 • UAT-006 • UAT-010 • UAT-022 | Open
UAT-D04 | FAS timing, routing and decision permissions | Select current F4/F5/F10 rules: form-close assessment/ranking vs immediate decision, HQ read-only vs decision authority, school routing, scheme criteria and application eligibility/duplicate/finality behavior. Confirm cross-school sibling selection in one family submission, per-child review/data visibility and the F5 at-least-one-child-at-submitting-school rule; do not impose a blanket other-school-sibling ban. | Gavin with Kent, Howard and BA | • SRC-FS • SRC-BACKLOG • SRC-TRANSCRIPT | • UAT-008 • UAT-028 • UAT-029 • UAT-031 • UAT-032 • UAT-034 • UAT-035 • UAT-036 | Open
UAT-D04 | FAS timing, routing and decision permissions | Select current F4/F5/F10 rules: form-close assessment/ranking vs immediate decision, HQ read-only vs decision authority, school routing, scheme criteria and application eligibility/duplicate/finality behavior. Confirm cross-school sibling selection in one family submission, per-child review/data visibility and the F5 at-least-one-child-at-submitting-school rule; do not impose a blanket other-school-sibling ban. | Gavin with Kent, Howard and BA | • SRC-FS • SRC-BACKLOG • SRC-TRANSCRIPT | • UAT-045 • UAT-046 • UAT-047 • UAT-048 • UAT-049 | Open
UAT-D05 | Budget accounting and grant policy | Resolve R6 warning-only versus backlog budget-blocking grant rule. Record budget period/edit rights, counting basis, remaining/negative amount and warning thresholds, with approver/source. | Gavin with BA and FAS/R6 Dev | • SRC-FS • SRC-BACKLOG | • UAT-034 • UAT-038 • UAT-039 • UAT-040 • UAT-045 | Open
UAT-D06 | FAS income, documents and monetary effects | Record household count/additional-income inclusion, document validation/retrieval failure behavior, rounding/caps/effective dates, paid charges and multiple grants. Check QA fixture arithmetic against selected rules. | Gavin with Howard/Kent and BA | • SRC-TRANSCRIPT • SRC-FS • SRC-BACKLOG | • UAT-008 • UAT-009 • UAT-028 • UAT-029 • UAT-030 • UAT-032 • UAT-033 • UAT-035 | Open
UAT-D06 | FAS income, documents and monetary effects | Record household count/additional-income inclusion, document validation/retrieval failure behavior, rounding/caps/effective dates, paid charges and multiple grants. Check QA fixture arithmetic against selected rules. | Gavin with Howard/Kent and BA | • SRC-TRANSCRIPT • SRC-FS • SRC-BACKLOG | • UAT-036 • UAT-037 • UAT-045 • UAT-046 • UAT-047 • UAT-049 | Open
UAT-D07 | View As behavior and safety contract | Scope is fixed View As. Confirm target/user authority, read-only server enforcement, banner/context, audit attribution, exit/session isolation and permitted fields. No general simulation engine added. | Chan with function owners, BA and Dev | • SRC-USER • SRC-VIEW | • UAT-041 • UAT-042 | Open
UAT-D08 | FAQ answer bank and help behavior | Scope is fixed simple system-use FAQ. Approve answer facts/revision, supported user/location/language, out-of-scope fallback and no private lookup/action; do not add an LLM or auto-fill requirement. | Howard with each function owner and BA | • SRC-USER • SRC-VIEW | • UAT-043 • UAT-044 | Open
UAT-D09 | Named delivery and execution authority | Record build/commit and QA URL, mock/dependency versions, authorized accounts, isolation/reset/date/fault/outcome-query controls, and named business acceptance representative/delegate. Product tests did not run during preparation. | Josh with Chan, PM/Dev and business representative | • SRC-USER • SRC-DEFECTS • SRC-S2 | • UAT-011 • UAT-012 • UAT-014 • UAT-024 • UAT-026 • UAT-037 • UAT-042 • UAT-045 | Open
UAT-D09 | Named delivery and execution authority | Record build/commit and QA URL, mock/dependency versions, authorized accounts, isolation/reset/date/fault/outcome-query controls, and named business acceptance representative/delegate. Product tests did not run during preparation. | Josh with Chan, PM/Dev and business representative | • SRC-USER • SRC-DEFECTS • SRC-S2 | • UAT-046 • UAT-047 • UAT-048 • UAT-049 | Open
UAT-D10 | School/fee effective dates and import contract | Select R3 variant and record transfer/enrolment effective dates, stage/category rate period/overlap rules, publication snapshot/replay, CSV row atomicity and optional-class behavior. | Kent and Chan with BA and Nito/Tyson | • SRC-FS • SRC-BACKLOG | • UAT-016 • UAT-017 • UAT-018 • UAT-020 • UAT-021 • UAT-045 | Open

## Readiness
ID | Check | Owner | Evidence needed | Status | Actual result
READY-01 | Every S1/S2 story and the two additions remain visible, with one owner and scenario mapping; current delivery mapping attached without silent exclusions. | Josh | Coverage sheet plus dated Sprint1/2 delivery mapping; explain retained R6 requirements and all 53 V3 stories. | Not checked
READY-02 | Each person completes their assigned business scripts and a different QA reviews them. | Kent / Chan / Howard / Gavin | Review record names author, reviewer, scenario IDs, version, issues and disposition. Kent/Chan pair; Howard/Gavin pair. Gavin reviews Josh. | Not checked
READY-03 | Business expected results are approved or affected scenarios clearly blocked; no feature is removed to resolve a rule conflict. | Josh with BA | UAT-D decision resolution with approver/date/source and affected script revision. Blank or Open is not approved. | Not checked
READY-04 | Named integrated build and external/mock identities are available. | Chan with Dev | Build/commit, QA URL, deployed components, dependency/mock versions and smoke results tied to current build. | Not checked
READY-05 | Synthetic roles/data and safe reset/date/fault controls work. | Chan with fixture owners | User mapping without credentials; fixture setup/read-back; before/after reset receipt; owned data isolation; successful control rehearsal. | Not checked
READY-06 | Critical end-to-end journeys have a rehearsal record or exact blocker on the candidate build. | Josh with journey owners | FAS online and paper, subsidy/charge/payment, lifecycle/top-up/history, View As and FAQ results with build/actor/date/evidence. No old diagnostic pass reuse. | Not checked
READY-07 | Financial, permission and prior blocking-defect regressions are checked before UAT entry. | Josh / Gavin / Chan | Current-build ledger/charge/payment reconciliation, family/school isolation, View As write prevention and targeted retest evidence; unresolved material failures block affected acceptance. | Not checked
READY-08 | Business session roles and acceptance authority are named. | Josh with PM/business representative | Business participants, authorized acceptance decision-maker/delegate, QA facilitator and recorder; acceptance authority is not inferred from QA attendance. | Not checked
READY-09 | Execution copy and evidence/result conventions are ready. | Howard | Run copy names build/date/version; each result has actor, actual, evidence, linked defects and unresolved limitations; Passed/Failed/Blocked/Not Run only. | Not checked
READY-10 | Wednesday preparation completion is reported honestly, without claiming execution/sign-off. | Josh | Reviewed pack, data/setup requirements, open-rule register and rehearsal/readiness report. Unready items listed with exact dependency/owner; future UAT results and business decision remain separate. | Not checked
EXIT-01 | All included business scenarios have an executed result and evidence on accepted build; no Not Run or unresolved rule counted as accepted. | Josh | Per-scenario result register, coverage gap report and business decision; incomplete variants remain visible. | Not checked
EXIT-02 | Blocking failures fixed/retested; any accepted residual risk is explicit and does not turn failed tests into passes. | Josh with authorized business owner | Defect/retest references and signed/acknowledged risk acceptance with exact affected scope; business may decline acceptance. | Not checked
EXIT-03 | Authorized business representative records accept, accept with named limitations, or reject. | Business representative, arranged by Josh | Dated build-specific decision and reasons. QA/BA rehearsal alone is not customer acceptance. | Not checked

## Sources
ID | Title | Locator | Standing | Checked | Limits
SRC-USER | Josh scope correction and Go | Current conversation, scope correction: all Sprint 1/2, View As for Function 7, simple system-use FAQ; subsequent Go authorizes local pack. | Current user instruction controls scope. It does not approve every draft business rule. | 2026-10-25 | No new customer sign-off, external filing, deployment or product execution.
SRC-BOARD | Agile Tracking Board PDF | ~/Downloads/Padlet - Agile Tracking Board.pdf, pages 1-5, QA assignments. PDF exported 25 October 2026. | Observed named historical task assignments; Done is board state, not execution evidence. | 2026-10-25, pdftotext -layout | Shows R3 Kent/Chan, R8 Howard, R9 Gavin, Chan environment/login automation, and R4 income-data Gavin. Does not allocate whole FAS UAT.
SRC-S2 | Sprint 2 Padlet PDF | ~/Downloads/Padlet - AGILE PADLET SPRINT 2.pdf, 22 October 2026, cards US-001 to US-053 across columns. | Dated planning and development status snapshot. | 2026-10-25, pdftotext -layout | Assignees are Dev, not QA. Ready for test and Done do not establish QA readiness.
SRC-BACKLOG | Product Backlog V3, 22 October capture | ../Team sources/2026-10-22-f2/sheet1.xlsx; Product Backlog rows 6-58, IDs US-001 to US-053; Acceptance Criteria rows 1-4. Live: https://docs.google.com/spreadsheets/d/1k7paZmnUG_2dl62q_9dYdMpcUgv9Lc2m/edit | Story identity and proposed outcomes. Acceptance Criteria sheet explicitly says none approved; Sprint values TBD. | 2026-10-25 local capture read | Not a current deployment/status check. US-001 feature title contains unrelated editorial text, so its title here comes from the story description and Sprint 2 card. Original file untouched.
SRC-MOM | Customer demo minutes, heading 19 October | https://docs.google.com/document/d/1V6f8hoe6rC8WZ_haJ5lvhM0LcguWrXX7n-In9TkXD6o/edit; agenda 1-7 | Live text export read during this conversation. Team-prepared meeting record, not a new approved specification. | 2026-10-25 | Header says 19 October, reference points to 23 October transcript, ending time also inconsistent. Ask minute owner to correct date, do not invent one.
SRC-TRANSCRIPT | Meeting Transcript, labelled 23 October 2026 | https://docs.google.com/document/d/1TYnZ44hcBkcycc6gcdY4W4RiFkIrSsMf/edit; 05:09-05:52 AAD, 09:11-09:45 FAS focus, 14:47-19:45 application feedback, 20:20-21:50 scope risk, 23:44-31:15 top-up. | Customer feedback as recorded in supplied transcript; speaker labels and unclear sections preserved. | 2026-10-25 | Scheduling and failed-only retry were requested; team promised assessment/solution, not a finalized implementation contract. No volume/SLA inferred from examples.
SRC-R1 | R1 v1.2 refinement draft, requested tab | https://docs.google.com/document/d/1k0xJrdGwCzFzfqVhofzwgRPcdvoV8O9DFtzWpq-_kjQ/edit?tab=t.5pdms31w4le; sections 1.1, 1.2, 2.3 and 4; captured copy ../Team sources/2026-10-22-f2/tab_t.5pdms31w4le.txt | Live tab re-read. CR/TD/WA and Deferred distinctions remain. | 2026-10-25 | CPF deferred in this Sprint 1 draft conflicts with Sprint 2 transfer delivery reports. R1 F02 is closure, not project R2 top-up.
SRC-FS | Agile FS complete dated text capture | ../Team sources/2026-10-22-f2/doc2.txt; R3 around lines 4800-6806, F4 v1.3 lines 6807 onward, F5 v1.2 lines 7311 onward, R6 lines 7539 onward. Tab map: F4 t.wxc52rfyyly, F5 t.tlktmn4sx46u, R6 t.19zirrjk6ccb, F9 t.duowzmhz1pzq, F10 t.qcf7b5ald42m. Live: https://docs.google.com/document/d/1k0xJrdGwCzFzfqVhofzwgRPcdvoV8O9DFtzWpq-_kjQ/edit | Dated drafts, with live tab titles/versions checked 25 October. Not every section is customer-approved. | 2026-10-25 | Multiple competing variants. F4 waits until form closes; R6 warns rather than blocks grants, unlike old backlog wording. Capture is evidence of wording, not version authority.
SRC-F2 | Function 2 plan/spec v1.2.1 and capture receipt | function-2-test-plan.md sections 2-3; ../Team sources/2026-10-22-f2/receipt.md; narrow F2 tab t.7jlsws8ic0aa, wider t.5k1d9kwak8ef. | Local proposed narrow baseline, not scope cancellation or customer acceptance. | 2026-10-25 | Conflicts on criteria AND/OR, budget, scheduling, correction, repeat execution. Existing deferred-case labels do not remove current pack scope.
SRC-VIEW | High-level solution, F7 and questions | ../Team sources/2026-10-22-f2/doc1.txt, lines 67-71 F7 View As and 124-129 questions. Live source recorded in capture receipt. | Proposed read-only View As, banner and logging support the QA safety expectations; current user fixes feature scope. | 2026-10-25 | Target permissions, endpoint enforcement, session/audit details still need behaviour confirmation. No general simulation engine is added.
SRC-DEFECTS | F2 current defect report | sprint-2/2026-10-23-f2-defects/f2-defects.md, Read before reproducing and active findings. | Historical diagnostics: clean build blockers and labelled patched-copy findings. Nine conditional findings remain conditional. | 2026-10-25 | Not rerun here. Never import old pass/fail outcomes into UAT; withdrawn claims remain withdrawn. Prior failures require retest on current delivery.