## EduFAMS Defect Log
EduFAMS Defect Log (Master QA Log with High-Clarity Visual Evidence)
Consolidated Defect Tracking: Chan (DEF-001 to DEF-015) & Kent Tran (DEF-016 to DEF-023) ¦ High-clarity cropped screenshots embedded directly in column 'Evidence'
Defect ID | Reported By | Defect Summary | Severity | Priority | Status | Defect Type | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Linked Test Case(s) | Evidence (Screenshot - High Clarity Zoom) | Notes
DEF-001 | Chan | Unable to click the Change button | TBD | High | Open | UI | EduFAMS Admin Portal — School Users | A school user row is displayed; screenshot shows USR-00002 (Bui Thi H). | 1. Open School Users. 2. Locate USR-00002 (Bui Thi H). 3. Click the pencil (Change/Edit) action. | The selected school user's edit form opens. | The pencil (Change/Edit) action cannot be clicked. | TBD |  | Screenshot highlights the pencil action for USR-00002. [Full: evidence/DEF-001_Evidence-01.png]
DEF-002 | Chan | Unable to click the Delete button | TBD | High | Open | UI | EduFAMS Admin Portal — School Users | A school user row is displayed; screenshot shows USR-00002 (Bui Thi H), unassigned to a school. | 1. Open School Users. 2. Locate USR-00002 (Bui Thi H). 3. Click the trash (Delete) action. | The delete confirmation or intended delete action is triggered. | The Delete button cannot be clicked. | TBD |  | Screenshot highlights the Delete action for USR-00002. [Full: evidence/DEF-002_Evidence-01.png]
DEF-003 | Chan | Import result column is labeled “Row” instead of “Number” | TBD | Low | Open | UI / Content | EduFAMS Admin Portal — School Users — Bulk create | The bulk import has completed and the Import result table is visible. | 1. Open School Users. 2. Go to Bulk create. 3. Import a CSV and review the Import result table. | The column identifying each CSV entry is labeled “Number”. | The column is labeled “Row”. | TBD |  | Screenshot shows the “Row” header and row indices in the import result table. [Full: evidence/DEF-003_Evidence-01.png]
DEF-004 | Chan | Invalid Year value displays a generic validation message | TBD | Medium | Open | Validation / UX | EduFAMS Admin Portal — Academic Years — Create | The Create an academic year form is open. | 1. Open Academic Years and select Create academic year. 2. Enter an invalid value such as `wwe` in Year. 3. Enter valid start and end dates. 4. Select Create academic year. | A clear, field-specific message explains the valid Year format and indicates the Year field needs correction. | The form displays “Unable to create academic year” with the generic message System.ValidationFailed; it does not explain what is invalid in Year. | TBD |  | Screenshot shows `wwe` in Year and the generic validation error. [Full: evidence/DEF-004_Evidence-01.png]
DEF-005 | Chan | Active class count is incorrect for FPT University — HCM City | TBD | High | Open | Data / Display | EduFAMS Admin Portal — School management | The school management list is displayed. | 1. Open School management. 2. Locate FPT University — HCM City (MOE code `FPT`). 3. Review its Active classes and Active students counts. | Active classes displays the correct count for the school; confirm the expected count against the school's class data. | Active classes displays 0 while Active students displays 30. | TBD |  | Screenshot highlights the Active classes value 0 for FPT. Expected count not provided. [Full: evidence/DEF-005_Evidence-01.png]
DEF-006 | Chan | Search students field is missing placeholder text | TBD | Low | Open | UI / Content | EduFAMS Admin Portal — Students | The Students page is open. | 1. Open Students. 2. Inspect the Search students input while it is empty. | The search field displays placeholder text that helps users understand what they can search for. | The empty Search students field has no visible placeholder text. | TBD |  | Screenshot shows the blank search input; expected placeholder wording not specified. [Full: evidence/DEF-006_Evidence-01.png]
DEF-007 | Chan | Fee batch search does not filter results | TBD | Medium | Open | Functional | EduFAMS Admin Portal — Fee Batches | Fee publication batches are listed. | 1. Open Fee Batches. 2. Enter `GOPs` in Search fee batches. 3. Select Search. | Results are filtered to batches matching `GOPs`. | Unrelated batch titles remain visible alongside the matching `GOPs` result. | TBD |  | Screenshot shows `GOPs` in the search field while `ffff332`, `Học Phí 2026`, and `ffff` remain in the results. [Full: evidence/DEF-007_Evidence-01.png]
DEF-008 | Chan | Unable to create fee publication when no active academic year exists | TBD | Medium | Open | Functional / Configuration | EduFAMS Admin Portal — Fee Batches — Create fee publication | The Create fee publication form is open; no active academic year is configured. | 1. Open Fee Batches and start creating a fee publication. 2. Enter the publication details and targets. 3. Submit the form. | The publication is created when valid required details are provided and an active academic year is configured, or the prerequisite is clearly explained before submission. | Creation fails with “Could not create fee publication” and “No active academic year.” | TBD |  | Screenshot shows the error with title `SOP900` and period/charge/due dates entered. [Full: evidence/DEF-008_Evidence-01.png]
DEF-009 | Chan | Fee publication batches page fails to load data | TBD | Urgent | Open | Backend / Data | EduFAMS Admin Portal — Fee Batches | The Fee publication batches page is opened. | 1. Open Fee Batches. 2. Wait for the publication batches list to load. | Fee batch data loads and the user can review the list. | The page shows “Unable to load data” with error `Invalid column name 'school_id'`. | TBD |  | The page offers a “Try again” action, but the displayed database column error prevents data from loading. [Full: evidence/DEF-009_Evidence-01.png]
DEF-010 | Chan | Fee management page fails to load fee types | TBD | Urgent | Open | Functional / Data | EduFAMS Admin Portal — Fee management | The Fee management page is opened. | 1. Open Fees. 2. Wait for fee type data to load. | Fee types and related fee management data are displayed. | The page shows “Unable to load data” and “Fee information could not be loaded. Try again.” | TBD |  | Screenshot shows the fee types search area and the load error with a “Try again” action. [Full: evidence/DEF-010_Evidence-01.png]
DEF-011 | Chan | Student import template shows the wrong date format | TBD | Medium | Open | UI / Content | EduFAMS Admin Portal — Students — Bulk import template | The student bulk import template is open in a spreadsheet application. | 1. Download and open the student bulk import template. 2. Review the Date of Birth and Enrollment Start column headers. | Both date columns specify the expected format mm/dd/yyyy. | The headers specify dd/mm/yyyy. | TBD |  | Screenshot shows dd/mm/yyyy for Date of Birth and Enrollment Start; expected format supplied as mm/dd/yyyy. [Full: evidence/DEF-011_Evidence-01.png]
DEF-012 | Chan | Unable to import students using the bulk student upload | TBD | Urgent | Open | Functional / Validation | EduFAMS Admin Portal — Students — Bulk creation | The Bulk student creation form is open and a student CSV file is selected. | 1. Open Students and select Bulk. 2. Choose the completed student import CSV. 3. Review the validation result. | A CSV using the provided student import template is accepted and proceeds to row review. | The upload is rejected with “Invalid student import template” and a message listing expected columns: Display Name, Student Nric, Date of Birth, Student Citizenship, Enrollment Start, and Class Code. | TBD |  | Screenshot shows Bulk_Students_Import_Template (1).csv selected and Submit students disabled. Priority marked Urgent per user. [Full: evidence/DEF-012_Evidence-01.png]
DEF-013 | Chan | Bulk class preview column is labeled “Row” instead of “No” | TBD | Low | Open | UI / Content | EduFAMS Admin Portal — Classes — Bulk creation | A class import CSV has been uploaded and the Preview and edit table is displayed. | 1. Open Classes and select Bulk. 2. Upload a class template CSV. 3. Review the Preview and edit table. | The row-number column is labeled “No”. | The column is labeled “Row”. | TBD |  | Screenshot shows the “Row” header and row numbers 2 and 3. Expected label supplied as “No”. [Full: evidence/DEF-013_Evidence-01.png]
DEF-014 | Chan | Academic level in bulk class preview is a text field instead of a dropdown | TBD | Medium | Open | UI / Usability | EduFAMS Admin Portal — Classes — Bulk creation | A class import CSV has been uploaded and the Preview and edit table is displayed. | 1. Open Classes and select Bulk. 2. Upload a class template CSV. 3. Review the Academic level control for a row. | Academic level is selected from a dropdown containing available academic levels. | Academic level is presented as a free-text input. | TBD |  | Screenshot shows text inputs containing Primary 1 and Primary 2 in the Academic level column. [Full: evidence/DEF-014_Evidence-01.png]
DEF-015 | Chan | Student profile does not display NRIC information | TBD | High | Open | Data / Display | EduFAMS Admin Portal — Students — Student profile | A student profile is open. | 1. Open Students. 2. Open the student profile (screenshot shows OP1). 3. Review the displayed student details. | The student's NRIC information is displayed in the profile, subject to the user's access permissions. | No NRIC field or value is visible in the profile details. | TBD |  | Screenshot shows student name, date of birth, category, school, class, and enrollment details, with no NRIC information. [Full: evidence/DEF-015_Evidence-01.png]
DEF-016 | Kent Tran | MOEFAS page fails to load schemes with HTTP 404 | Blocker | Urgent | Open | Backend / API | EduFAMS Admin Portal — FINANCIAL — MOEFAS | Logged in as MOE HQ Administrator (admin@IAM.edu.vn). | 1. Open Admin Portal. 2. Under FINANCIAL in sidebar, select MOEFAS (/moefas). 3. Review page load and network response. | The page loads available MOEFAS schemes from backend or renders a clean empty state with a 'New scheme' button (HTTP 200). | API call GET /api/fas/v1/fas/moe-schemes fails with HTTP 404. Page displays red error alert: “Unable to load data: The MOEFAS schemes could not be loaded. Please try again.” | TS-R4-FAS-001 |  | Backend controller route unmapped or Vite proxy misconfigured for /api/fas/. Fatal client demo breaker. [Full: evidence/DEF-016_Evidence-01.png]
DEF-017 | Kent Tran | Navigation sidebar exposes unbuilt scaffold placeholder pages and dashboard header typo | Major | High | Open | UI / Content | EduFAMS Admin Portal — Top-up, FAS & Root Dashboard | Admin portal is opened under any administrative role. | 1. Log in to Admin Portal and inspect root header. 2. Select EDUSAVE -> Top-up. 3. Select FINANCIAL -> FAS. | Dashboard displays production widgets with correct spelling 'Financial'. Unreleased modules are hidden from sidebar navigation. | Root dashboard header displays “Education Fanancial Account Management System” (spelling error) and body says “This feature is scaffolded...”. Both /top-up and /fas display blank scaffold cards. | TS-R3-DASH-001 |  | Needs typo fix in translation.json ('Fanancial' -> 'Financial') and feature-flag hiding in manifests. [Full: evidence/DEF-017_Evidence-01.png]
DEF-018 | Kent Tran | MOE HQ role is bounced with Access Restricted error upon accessing Class Management | Major | Medium | Open | Routing / Security Guard | EduFAMS Admin Portal — Class Management | Logged in as MOE HQ Administrator (admin@IAM.edu.vn). | 1. Log in as MOE HQ Admin. 2. Navigate directly to /class-management (or click class link from school overview). | MOE HQ is granted read-only auditing access across all school classes, or presented with an informative 403 / role switch screen. | Router guard blocks access, flashes red toast “Access restricted: Your account does not have permission...”, and bounces user to root dashboard. | TS-R3-F04-001 |  | class-management/manifest.ts restricts access to SCHOOL only, trapping MOE HQ users. [Full: evidence/DEF-018_Evidence-01.png]
DEF-019 | Kent Tran | Fee Batches table and detail view render raw technical GUIDs instead of human-readable names | Moderate | Medium | Open | UI / Data Display | EduFAMS Admin Portal — Fee Batches | Completed or draft fee publication batches exist in the system. | 1. Open Fee Batches. 2. Review Fee Component column. 3. Select View details on a batch. 4. Review Fee Component and Created by fields. | Fee Component displays friendly component name (e.g., “Standard Miscellaneous Fee”) and Created by displays admin name/email. | Table and details display raw GUIDs ffff0001-0000-0000-0000-000000000002 and 01A159A5-0F27-.... Details view also lacks student charges sub-table. | TS-R3-F12-003 |  | Requires entity lookup/join against fee component and user tables before rendering. [Full: evidence/DEF-019_Evidence-01.png]
DEF-020 | Kent Tran | Newly created student displays raw database UUID instead of standard STU-xxx format | Moderate | Low | Open | Data / Display | EduFAMS Admin Portal — Students | The Create student form is completed and submitted. | 1. Open Students and select Create student. 2. Create student Lucas Tan Wei Jie. 3. Review the student management table and student profile header. | System assigns a standardized business code (e.g. STU-00005) consistent with baseline records (STU-001, STU-003). | Table and profile header display full database UUID Lucas Tan Wei Jie f73e9aa4-0143-4826-9e48-93e184200d07. | TS-R3-F05-002 |  | Needs sequential business code generator in StudentSchoolService on record persistence. [Full: evidence/DEF-020_Evidence-01.png]
DEF-021 | Kent Tran | Database contains invalid test mock student (Age 25 in Primary 2 with corrupted class code) | Moderate | Low | Open | Data / Sanitation | EduFAMS Admin Portal — Students | Logged in as School User for Rosyth Primary School (staff1@IAM.edu.vn). | 1. Open Students. 2. Inspect student row for Trần Tuấn Kiệt. 3. Review Date of Birth, Category, and Class. | All mock student records reflect valid primary school age limits (Ages 6–12) and valid class names. | Record shows DOB May 18, 2001 (Age 25 in primary school) assigned to class 111111111111111111 · P2-X. | TS-R3-F05-DATA |  | Dirty test mock data in StudentSchoolDatabase.dbo.students. Needs purge script. [Full: evidence/DEF-021_Evidence-01.png]
DEF-022 | Kent Tran | Parent portal child profile card displays truncated age label missing numerical value | Minor | Low | Open | UI / Content | EduFAMS Parent Portal E-Service — Dashboard | Logged in as verified parent via SingPass MockPass (e.g., S7890123F - NGUYEN VAN MINH). | 1. Access Parent Portal (http://localhost:5174/). 2. Authenticate as parent. 3. Review the child Education Account card header. | Card header displays formatted age integer (e.g., EDU-00172 · Age 11 · Active). | Numerical age is omitted, literally displaying EDU-00172 · Age Active. | TS-R9-PARENT-001 |  | Missing age integer in React JSX template string interpolation. [Full: evidence/DEF-022_Evidence-01.png]
DEF-023 | Kent Tran | FAS application submitted by parent has no review or approval queue in Admin Portal | Major | High | Open | Functional / Workflow | EduFAMS Parent Portal & Admin Portal | Parent has submitted a financial assistance application on Parent Portal (/fas/apply). | 1. Complete and submit FAS application on Parent Portal. 2. Log in to Admin Portal as School Clerk or MOE HQ. 3. Attempt to locate incoming application for verification. | Submitted applications appear in an administrative queue for review, document verification, and approval/rejection. | Admin Portal /fas is a blank placeholder card and /moefas fails with 404; submitted applications cannot be audited or actioned via UI. | TS-R4-FAS-FLOW |  | Broken end-to-end integration between apps/parent-portal intake and apps/admin-portal back-office review. [Full: evidence/DEF-023_Evidence-01.png]